## VO
Variation Order 1
VO FOR FINAL MEASUREMENT
A) OMISSION
1. Internal Wall Finishes
Wall tile. c/w cement backings
1.1 TW1 - white horse 300mm x 300mm C30000 | m2 | -667.2 | 22.6
1.2 TW2 - white horse 300mm x 300mm C30062 | m2 | -3933.08 | 22.6
2. Internal Floor Finishes
2.1 Cement and sand renderings to floor (TF5) | m2 | -442.8 | 10.5
2.2 Floor tiles on screeds including tile skirtings and drops
2.2.1 TF2 - white horse 300mm x 300mm C 30059 - general | m2 | -1312.8 | 19.4
2.2.2 TF4 - white horse 500mm x 500mm C 50015 - general | m2 | -13194.56 | 21.5
2.2.3 TF4 - white horse 500mm x 500mm C 50015 - skirting | m | -12292.32 | 3.9
2.2.4 TF4 - white horse 500mm x 500mm C 50015 - 100mm drop | m | -567 | 3.9
2.2.5 TF4 - white horse 500mm x 500mm C 50015 - 50mm drop | m | -300 | 3.9
2.2.6 TF2 - white horse 300mm x 300mm C 30062 - general | m2 | -53.96 | 19.4
2.2.7 TF2 - white horse 300mm x 300mm C 30062 - skirting | m | -12.6 | 3.9
2.2.8 To install floor trap complete with tiles shaping | nos | -906 | 5
3. Staircase Finishes
Floor tiles on screed including tile to tread, riser and landing slab
3.1 TF4 - white horse 500mm x 500mm C 50015 to landing slab | m2 | -122.04 | 27
3.2 TF4 - white horse 500mm x 500mm C 50015 - 270mm high | m | -2157.84 | 13.5
3.3 TF4 - white horse 500mm x 500mm C 50015 - 170mm high | m | -2157.84 | 13.5
3.4 Forming nosing tiles | m | -2153.52 | 7.54
4. External Floor Finish
4.1 Cement and sand paving troweled smooth to floor
cement rendering
4.1.1 On air-con ledge & water tank | m2 | -925.4 | 13
4.1.2 A1 apron slab, courtyard @ ground floor | lump sum | -2 | 330
4.1.3 A2 apron slab @ ground floor | lump sum | -8 | 130
4.1.4 B1/B1a apron slab @ ground floor | lump sum | -4 | 270
4.1.5 B2 apron slab @ ground floor | lump sum | -14 | 100
4.1.6 C1/C1a apron slab @ ground floor | lump sum | -24 | 240
4.1.7 C2/C2a apron slab @ ground floor | lump sum | -84 | 80
4.2 broom finish | m2 | -6578.8 | 13
4.3 Floor tiles on screeds including tile skirtings and drops
4.3.1 TF4 - white horse 500mm x 500mm C 50015 - general | m2 | -225.3 | 21.5
4.3.2 TF4 - white horse 500mm x 500mm C 50015 - skirting | m | -274.56 | 3.9
5. Others
5.1 Sliding door kerb | m | -277.2 | 7.8
5.2 Refuse chamber wall/floor tiles with screed 300x300
5.2.1 wall | m2 | -510 | 22.6
5.2.2 floor | m2 | -156.4 | 19.4
B) ADDITION
1. Internal Wall Finishes
Wall tile. c/w cement backings
1.1 TW1 - white horse 300mm x 300mm C30000 | m2 | 879.84 | 22.6
1.2 TW2 - white horse 300mm x 300mm C30062 | m2 | 3835.78 | 22.6
2. Internal Floor Finishes
2.1 Cement and sand renderings to floor (TF5) | m2 | 336.96 | 10.5
2.2 Floor tiles on screeds including tile skirtings and drops
2.2.1 TF2 - white horse 300mm x 300mm C 30059 - general | m2 | 1262.66 | 19.4
2.2.2 TF4 - white horse 500mm x 500mm C 50015 - general | m2 | 13234.92 | 21.5
2.2.3 TF4 - white horse 500mm x 500mm C 50015 - skirting | m | 10855.63 | 3.9
2.2.4 TF4 - white horse 500mm x 500mm C 50015 - 100mm drop | m | 477.93 | 3.9
2.2.5 TF4 - white horse 500mm x 500mm C 50015 - 50mm drop | m | 831.8 | 3.9
3. Staircase Finishes
Floor tiles on screed including tile to tread, riser and landing slab
3.1 TF4 - white horse 500mm x 500mm C 50015 to landing slab | m2 | 129.6 | 27
3.2 TF4 - white horse 500mm x 500mm C 50015 - 270mm high | m | 1881.36 | 13.5
3.3 TF4 - white horse 500mm x 500mm C 50015 - 170mm high | m | 2128.68 | 13.5
4. External Floor Finish
4.1 Cement and sand paving troweled smooth to floor
cement rendering
4.1.1 On air-con ledge & water tank | m2 | 594.08 | 13
4.1.2 A1 apron slab, courtyard @ ground floor | lump sum | 2 | 330
4.1.3 A2 apron slab @ ground floor | lump sum | 8 | 130
4.1.4 B1/B1a apron slab @ ground floor | lump sum | 4 | 270
4.1.5 B2 apron slab @ ground floor | lump sum | 14 | 100
4.1.6 C1/C1a apron slab @ ground floor | lump sum | 24 | 240
4.1.7 C2/C2a apron slab @ ground floor | lump sum | 84 | 80
5. Others
5.1 Sliding door kerb | m | 301.06 | 7.8
5.2 Refuse chamber wall/floor tiles with screed 300x300
5.2.1 wall | m2 | 334.56 | 22.6
5.2.2 floor | m2 | 50.32 | 19.4
Variation Order 2
VO FOR INSTALLATION OF TOILET PAPER HOLDER
2 nos per unit for 28 units of 1-storey and 3 nos per unit for 108 units of 2-storey
A) OMISSION
B) ADDITION
1. Installation of toilet paper holder | nos | 380 | 15