## VO1 (2)
Variation Order 01
To Supply and Install - Mild Steel Railing At Balcony
Awarded Qty /(Omission)
Design, supply and install of the steel of the steel roof structure and steel column completed with the RHS SHS, bracing , ms plate , bolt , nut , painting and others necessary items.
80mm ext dia x 5mm thk ms post welded (column) | No | 150 | -30 | 150 | -30
2'' x 4'' x 5mm thk RHS (Beam) | M | 65 | -90 | 65 | -90
175mm x 175mm x 10 thk M.S. Plate c/w 4 no 12 dia M.S. Bolt | No | 25.5 | -90 | 25.5 | -90
Mild Steel Railing At Balcony - Approximately 1050mm high mild steel hollow section consisting of 50mm x 25mm x 1.2mm thk m.s. R.H.S. vertically at every 1000mm centre to centre, 32mm x (1.2-1.6)mm thk. m.s. strip vertically every 100mm centre to centre, 65mm x 38mm x 1.6mm thk. m.s. R.H.S. top horizontally and 38mm x (1.6-2.3)mm thk. m.s. strip bottom horizontally including welding, painting and including all necessary works; allas per Architect's detail and approval | M | 109 | -20 | 109 | -20
( Actual On site )
80mm ext dia x 5mm thk ms post welded (column) | No | 150 | 30 | 150 | 30
2'' x 4'' x 5mm thk RHS (Beam) | M | 65 | 90 | 65 | 90
175mm x 175mm x 10 thk M.S. Plate c/w 4 no 12 dia M.S. Bolt | No | 25.5 | 90 | 25.5 | 90
Mild Steel Railing At Balcony - Approximately 1050mm high mild steel hollow section consisting of 50mm x 25mm x 1.2mm thk m.s. R.H.S. vertically at every 1000mm centre to centre, 32mm x (1.2-1.6)mm thk. m.s. strip vertically every 100mm centre to centre, 65mm x 38mm x 1.6mm thk. m.s. R.H.S. top horizontally and 38mm x (1.6-2.3)mm thk. m.s. strip bottom horizontally including welding, painting and including all necessary works; allas per Architect's detail and approval | M | 109 | 7 | 109 | 7