## Sheet1
ALUNAN ASAS SDN BHD (257699-V)
CADANGAN 1 BLOK BANGUNAN PERNIAGAAN 30 TINGKAT (425 BILIK HOTEL) DENGAN 1 TINGKAT SUB-BASEMENT YANG MENGANDUNGI:-
1) 1 TINGKAT RUANG SERVIS HOTEL DI TINGKAT BAWAH TANAH
2) 1 TINGKAT KEMUDAHAN SOKONGAN HOTEL DAN PENCAWANG ELEKTRIK DI TINGKAT 1
3) 1 TINGKAT PEJABAT DI TINGKAT 1M
4) 1 TINGKAT KEMUDAHAN SOKONGAN HOTEL DI TINGKAT 2
5) 7 TINGKAT TEMPAT LETAK KERETA DAN RUANG MEKANIKAL DI TINGKAT 3 HINGGA TINGKAT 9
6) 1 TINGKAT DEWAN BANKUET HOTEL DI TINGKAT 10
7) 1 TINGKAT RESTORAN, PEJABAT DAN RUANG DAN MEKANIKAL DI TINGKAT 11
8) 1 TINGKAT ‘EXECUTIVE LOUNGE’, KOLAM RENANG KEMUDAHAN SOKONGAN HOTEL DI TINGKAT 12
9) 1 TINGKAT RUANG MEKANIKAL DI TINGKAT 13
10) 17 TINGKAT HOTEL (425 BILIK) DI TINGKAT 14 HINGGA 30
DI NO.6, JALAN SETIA DAGANG AH U13/AH, SETIA ALAM, SEKSYEN U13, 40170 SHAH ALAM, SELANGOR DARUL EHSAN.
Project | : TOP VALUE HOTEL ,SETIA ALAM
Re | : Supply and Install Operable Partition Walls
Mr Tan 019-3261 888
Item | Description | Unit | QTY | Megafold Corporation Sdn Bhd |  | WORKDONE
|  |  |  | Rate | Amount | Previous | Current | Accumulated | WD% | Amount
Operable Partition Walls
276200.0007
PARTITIONS
Supply and erect sliding and folding moveable aluminium frame partition to Architect selection and approved system: consists of tracks including bracket, hangers,guides,pivot, concrete, hinges, channels, ironmongery and all neccesary fixing accessories including infiling with sound insulation to achieve 50 STC requirement, with Architect selection and approved finishing, al las per manufactuer's specification and to Architect approval and satisfication in completion (Type 7)
1 | Overall size 24m length x 8.10m high (194.4m2 / AA Cost rate RM 1184.03/m2) | No | 1 | 156791.237 | 156791.237 | 0.8 | 0.2 | 1 | 100% | 156791.237
2 | Ditto, overall size 13.50m length x 8.10m high (109.35m2 / AA Cost rate RM 1184.03/m2) | No | 1 | 88660.1106 | 88660.1106 | 0.8 | 0.2 | 1 | 100% | 88660.1106
Sound Barrier Partition
To supply and install Plenim Sound Barrier above ceiling Construct with 2 layers of 12mm thick gypsum board each and metal stud framing and seal air tight
3 | Overall size 26,491mm (L) x 2,728mm (H) (72.27m2) | m2 | 73 | 206.1863 | 15051.6002 | 59.9388 | 13.0612 | 73 | 100% | 15051.6002
4 | Overall size 13,470mm (L) x 2,728mm (H) (36.75m2) | m2 | 37 | 206.1863 | 7628.8932 | 30.5435 | 6.4565 | 37 | 100% | 7628.8932
Others
5 | Acoustic Door ; to ceiling height | No | 3 | 2689.3866 | 8068.1597 | 2.4765 | 0.5235 | 3 | 100% | 8068.1597
6 | SST 5% | No | 1 | Included | Included | 1 | 0 | 1 | 60% | Included
| Summary | [5 empty] | Summary
2021-01-22
A | Operable Partition Walls |  |  |  |  | A | Operable Partition Walls |  |  |  | 2021-03-07
1 | Operable Partition Walls |  |  | - | 276200.0007 | 1 | Operable Partition Walls |  |  | 0
| Total Amount (RM) |  |  |  | 276200.0007 |  | Total Amount (RM) |  |  | 276200.0007
[9 empty] | VO | 36196.4942
[9 empty] | -5% | -15619.8247
296776.6702
[9 empty] | +downpayment | 55240
352016.6702
[9 empty] | -previous payment | -210593.67
[9 empty] | -downpayment | -55240
86183.0002

## VO
No | Description | Unit | Qty | Rate | Amount | Previous | Current | Total | Amount
PARTITIONS
Supply and erect sliding and folding moveable aluminium frame partition to Architect selection and approved system: consists of tracks including bracket, hangers,guides,pivot, concrete, hinges, channels, ironmongery and all neccesary fixing accessories including infiling with sound insulation to achieve 50 STC requirement, with Architect selection and approved finishing, al las per manufactuer's specification and to Architect approval and satisfication in completion (Type 7)
1 | Overall size 24m length x 8.10m high (194.4m2 / AA Cost rate RM 1184.03/m2) | No | 1 | 9928.44 | 9928.44 |  | 1 | 1 | 9928.44
2 | Ditto, overall size 13.50m length x 8.10m high (109.35m2 / AA Cost rate RM1184.03/m2) | No | 1 | 1670.13 | 1670.13 |  | 1 | 1 | 1670.13
Sound Barrier Partition
To supply and install Plenim Sound Barrier above ceiling Construct with 2 layers of 12mm thick gypsum board each and metal stud framing and seal air tight
3 | Overall size 26,491mm (L) x 2,728mm (H) (72.27m2) | m2 | 4 | 206.19 | 824.76 |  | 0 | 0 | 0
4 | Overall size 13,470mm (L) x 2,728mm (H) (36.75m2) | m2 | 5 | 206.19 | 1030.95 |  | 0 |  | 0
Others
5 | Acoustic Door ; to ceiling height | No | 3 | 206.19 | 618.57 |  | 2.8999 | 2.8999 | 597.9242
6 | Additional Storage Track | No | 1 | 15000 | 15000 |  | 1 | 1 | 15000
7 | Additoinal Box-up Stacking | No | 1 | 9000 | 9000 |  | 1 | 1 | 9000
| Total |  |  |  | 38072.85 |  |  |  | 36196.4942