## Sheet1
Drainage
Precast concrete box culvert nominal size 600mm x 600mm laid on 50mm thick lean concrete, min 300mm thick hardcore, 230mm thick concrete foundation with 1 layer of BRC A6 complete with precast cover concrete lid, laid in trench including all necessary excavation, formwork and hoisting; all as per Engineer's dwg and approval | M | 42 | 290.7 | 23 | 39.5
Precast concrete entrance culvert nominal size max 1.50 x600mm laid on 50mm thick lean concrete, min 300mm thick hardcore, 300mm concrete foundation with 1 layer of BRC B7 complete with 100mm thick concrete cover with BRC B7, 230mm thick brickwall thick brickwall, 50mm diameter groove line and including all necessary excavation, formwork and hoisting; all as per Engineer's dwg and approval | M | 17 | 431.775 | 17 | 52
Sump
Sump of internal dimension 1050mm x 1050mm x max 1800mm deep; constructed of 230mm thick concrete base with one layer of BRC B6, 230mm thick hardcore, 50mm thick lean concrete, sump wall comprises of 230mm thick well burnt clay brick laid in cement mortar (1:3) and 12.5mm thick plastering to expose surfaces, complete with openable FRP grating (measured separately), place on top of 150mm thick concrete slab with reinforcement, including all necessary excavation, formwork and forming outlets; all as per Engineer's detail dwg and approval | No | 7 | 1308.15
Ditto : 750mm x 750mm ; ditto | No |  |  | 3 | 450
Ditto : 600mm x 600mm ; ditto | No |  |  | 16 | 350
Drainage
300mm wide (internal) half round precast concrete "U" - shape drain average depth 1350mm deep laid on 150mm thick hardcore and 50mm thick lean concrete as base, drain slab and wall comprise of 150mm thick concrete slab and 150mm thick concrete slab and wall with one layer of BRC B5, 100mm diameter PVC weepholes at 1200mm centre to centre including 300mm x 300mm crusher run wrap with wire mesh of weepholes to be staggered, forming holes and connections to other works, 150mm x 150mm gap at 2000mm centre to centre and including all necessary works; all as per Engineer's detail dwgs and approval | M | 373 | 357.39 | 306 | 49
450mm wide (internal) half round precast concrete " U" - shape average depth 1350mm deep; ditto | M | 320 | 369.36 | 384 | 59
Cascading Drain
300mm wide (internal) half round precast concrete "U'- shape drain 'average depth 1350mm deep drop 0.15m every 2693mm centre to centre, laid on 150mm thick hardcore and 50mm thick lean concrete as base, drain slab and wall comprise of 150mm thick concrete slab and wall with one layer of BRC B5, 100mm diameter PVC weepholes at 1200mm centre to centre including 300mm x 300mm x 300mm crusher run wrap with wire mesh of weepholes to be staggered, forming holes and connections to other works 150mm x 150mm gap at 2000mm centre to centre and including all necessary works; all as per Engineer's detail dwgs and approval | M | 28 | 372.78 | 28 | 72
450mm wide ( internal ) half round precast concrete "U" - shaped drain average depth 1350mm deep drop 0.15m every 10008mm centre to centre; ditto | M | 197 | 373.212 | 65 | 78
Ditto; drop 0.15m every 9548mm centre to centre: do | M | 39 | 373.635 | 48 | 78
Ditto; drop 0.15m every 4389mm centre to centre: do | M | 101 | 378.765 | 77 | 85
Ditto; drop 0.15m every 2114mm centre to centre: do | M | 97 | 389.457 | 53 | 92
Ditto; drop 0.15m every 2072mm centre to centre: do | M | 66 | 389.88 | 56 | 92
Ditto; drop 0.15m every 2061mm centre to centre: do | M | 47 | 389.88 | 40 | 92
Ditto; drop 0.15m every 2036mm centre to centre: do | M | 22 | 389.88 | 15 | 92
Ditto; drop 0.15m every 2030mm centre to centre: do | M | 42 | 390.312 | 28 | 92
Ditto; drop 0.15m every 1918mm centre to centre: do | M | 50 | 391.59 | 50 | 92
Ditto; drop 0.15m every 1868mm centre to centre: do | M | 39 | 392.445 | 34 | 92
Ditto; drop 0.15m every 1708mm centre to centre: do | M | 40 | 394.155 | 32 | 92
Precast Concrete Slab Cover Drain
75mm thick x 600mm wide precast concrete slab cover drain comprises of one layer of BRC A7, reinforcement and including formwork, concrete and all necessary works; all as per Engineer 's detail dwg and approval | M | 189 | 23.94 | 168 | 22
Cattle Trap
Supply labour and material to construct completely cattle trap overall size 700mm wide x 600mm high comprises 225mm thick well compacted crusher run, 50mm thick lean concrete reinforcement T10 @ 100 centre to centre and T10 @ 200 centre to 'centre, 'formwork'eavy-duty grating (measured seprately) and including all necessary works all as per Engineer's dwg and approval | M | 133 | 311.22 | 104 | 72
Scupper Drain
Supply labour and material to construct completely scupper drain scupper drain 450mm x 175mm, comprises of 400mm x 400mm x 75mm precast concrete cover and 600mm x 600mm x 100mm precast concrete slab and 150mm thick wall with BRC A6, 50mm thick lean concrete, concrete, formwork and all necessary works; all as per Engineer's dwgs and approval | M | 45 | 44.46 | 43 | 33