## VO.6
Variation Order 06
Omission
Sub BQ | L/S | -1 | 2282888.29 | -1 | 2422855.8
VO1 | L/S |  |  | -1 | 25165
VO2 | L/S |  |  | -1 | 208679.76
VO3 | L/S |  |  | -1 | 77229.8
VO4 | L/S |  |  | -1 | 111996.54
VO5 | L/S |  |  | -1 | 15000
Addition
General
Note: Excavation for caisson piles to be commenced from the proposed platform levels. All overburden soil and rock above platform level to be cleared and strongly secured by maincon against land slide prior to commencement of caisson works. All quantites are provisional excluding survey and insurances.
Preliminaries and provision of all necessary labour, plants, equipment, pneumatic tools | LS | 1 | 56350 | 1 | 15000
and other accessories, transportation, dismantling and removal upon completion site
operation
Pressure grouting to stabilize unstable ground to facilitate caison shaft excavation works | Bag | 1 | 36 |  | 38
using 50kg per bag OPC cement (if necessary only) (rate only)
Administration and liaison fees incurred by local authorities (JMG, Police & etc) | Item | 1 | 14546 | 1 | 8000
in provision of permits related to use of explosives, monitoring and security escort during
the blasting operation
Note:
Provide insurance covers including CAR and workmen`s compensation (by main-con)
Carry out setting out and as-built survey (by main-con)
Site accomdation for workers and electricity power supply for night work if necessary (by main-con)
Remove excavated surplus and spoils and dispose away from site (by main-con)
Supply materials (steelbars/OPC/ready mixed cement) on contra account basic. (by main-con)
Demolish caisson lining above finished casting level concrete cover for all size of caissons (by main-con)
JKP New Compulsory Requirement - Appointment Of Licensed AGT who registered with JKKP to conduct gas tester before commencement of caisson on job requirement basic working in confine space. (part time only) (rate only) | Trip |  |  |  | 600
Earthwork
Plot 17 - 1000mm dia caisson pilling (20 nos)
Allow for the movements and set up of plants and equipment on the caisson foundation | No |  |  | 18 | 100
positions.
Allow for the movements and set up hoisting equipments on the caisson foundation positions - 1200mm into diameter caisson (Retaining A8) | No | 11 | 100
Construct concrete aprons to the approval of the Engineer to 1000mm diameter
caisson opening
1000mm caisson pile (P1) | No |  |  | 18 | 105
Construct concrete aprons to the approval of the Engineer to 1200mm diameter caisson (retaining A8) | No | 11 | 105
Excavation only through whatever soil strata except rock, the following diameters for hand
dug caissons, remove excavated materials, deposits, spread and level where directed
within the site including casting 75mm to 150mm thick concrete lining for caissons
Not exceeding 1.5m deep
1000mm dia caisson | M |  |  | 27 | 300
1200mm dia caisson (retaining A8) | M | 16.5 | 360
Exceeding 1.5m but not exceeding 3.0m deep
1000mm dia caisson | M |  |  | 27 | 310
1200mm dia caisson (retaining A8) | M | 16.5 | 360
Exceeding 3.0m but not exceeding 4.5m deep
1000mm dia caisson | M |  |  | 24.9 | 320
1200mm dia caisson (retaining A8) | M | 16.5 | 400
Exceeding 4.5m but not exceeding 6.0m deep
1000mm dia caisson | M |  |  | 24 | 330
1200mm dia caisson (retaining A8) | M | 16.5 | 400
Exceeding 6.0m but not exceeding 7.5m deep
1000mm dia caisson | M |  |  | 24 | 340
1200mm dia caisson (retaining A8) | M | 16.5 | 440
Exceeding 7.5m but not exceeding 9.0m deep
1000mm dia caisson | M |  |  | 19.72 | 350
1200mm dia caisson (retaining A8) (rate only) | M | 1 | 440
Exceeding 9.0m but not exceeding 10.5m deep
1000mm dia caisson | M |  |  | 13.78 | 360
Exceeding 10.5m but not exceeding 12.0m deep
1000mm dia caisson | M |  |  | 1 | 380
Exceeding 12.0m but not exceeding 13.5m deep
1000mm dia caisson | M |  |  | 1 | 400
Exceeding 13.5m but not exceeding 15.0m deep
1000mm dia caisson | M |  |  | 1 | 420
Exceeding 15.0m but not exceeding 16.5m deep
1000mm dia caisson | M |  |  | 1 | 440
Exceeding 16.5m but not exceeding 18.0m deep
1000mm dia caisson | M |  |  | 1 | 460
Exceeding 18.0m but not exceeding 19.5m deep
1000mm dia caisson | M |  |  | 1 | 480
Exceeding 19.5m but not exceeding 21.0m deep
1000mm dia caisson | M |  |  | 1 | 500
Extra over excavation through rock or bouldersin the following diamter caisson by using
explosive, break up, get up remove excavate rock deposit, spread and level where
directed within the site
1000mm diameter caisson (allow 3m rock only) | M |  |  | 135.95 | 638.7
Extra over for breaking through rock boulders and other obstuction by control rock blasting and pneumatic tools for touch up, get out and remove debris from site to contractor`s own deump within site (17m3/ caisson) (retaining A) | M3 | 198 | 425
Extra over for forming 1.0m belled out at the bottom of caisson
1000mm diameter caisson to 1400mm base dia (As per Mr Goh Great Soil no need according to drwg) | No |  |  | 1 | 450
Exc and breaking into rokcs to form socket by control rock blasting and pneumatic tools for touch up, get out debris from site to contractor`s own dump within the site (not exceeding 1.0m socketing) (retaining A8) | No | 11 | 380
Vibrated reinforcement concrete (Grade 30) tremie 1 as specified in caisson shaft (inclusive
overcasting 500mm) to
1000mm dia caisson | M |  |  | 141.63 | 260
1200mm internal diameter caisson (retaining A8) | M | 82.5 | 360
Extra over for bell out to 1000mm dia caisson (As per Mr Goh Great Soil no need according to drwg) | No |  |  |  | 300
Extra for forming 1600mm diameter bellout (retaining A8) | No | 11 | 320
Supply, fabricate and place steel reinforcement cage of following size and
installation of:
1000mm dia caisson
12Y25mm ditto (inclusive 1.0m starter bar) (416.45kg/no) | Kg |  |  | 13585.89 | 3.7
Y25mm ditton (retaining A8) | Kg | 7253.14 | 3.7
R10 at 300 c/c spiral link (1850kg/no) | Kg |  |  | 1768.15 | 3.8
12mm R-bar at 300mm c/c as link bars (retaining A8) | Kg | 718.17 | 3.8
Penetration drill test into bedrock at toe of caisson as directed by the S.O with pneumatic | No |  |  |  | 320
rock drill for a maximum depth of 4.5m, commencing at base of shaft, keeping records,
subsequently pressure grout up in cement and sand
ditto 1200mm (retaining A8) | No | 11 | 320
Allow for submission of caisson records in triplicate duly signed by contractor and the | Item | 1 |  | 1
S.O'`s representative and delivered to the S.O/Engineer as the work proceeds. (included)
Constuction of extension circular columns from caisson head to capping beam | M |  |  |  | 780
level. Rate inclusive formworks, rebar and G30 concrete tremie 1 and fixing and
dismantling moulds.
Supply and install 2T16 starter bar at 0.5m c/c. Rate inclusive epoxy grout (Hilti) | No |  |  |  | 38
and drilling as per details.
Apply sprayed concrete (gunite) 200mm thick c/w 2 layers of BRC A8 and 2 rows | M2 |  |  |  | 260
75mm dia. Weepholes to inter space of caissons. Rate including mob and demob.
Supply and construct 1000x1200mm capping beams rate inclusive formworks and | M |  |  |  | 680
rebar works
Earthwork (Cont`d)
Plot 11 - 1000mm dia caisson pilling (28 nos) transfer to vo.3
Allow for the movements and set up of plants and equipment on the caisson foundation | No |  |  |  | 100
positions.
Construct concrete aprons to the approval of the Engineer to 1000mm diameter
caisson opening
1000mm caisson pile (P1) | No |  |  |  | 105
Excavation only through whatever soil strata except rock, the following diameters for hand
dug caissons, remove excavated materials, deposits, spread and level where directed
within the site including casting 75mm to 150mm thick concrete lining for caissons
Not exceeding 1.5m deep
1000mm dia caisson | M |  |  |  | 300
Exceeding 1.5m but not exceeding 3.0m deep
1000mm dia caisson | M |  |  |  | 310
Exceeding 3.0m but not exceeding 4.5m deep
1000mm dia caisson | M |  |  |  | 320
Exceeding 4.5m but not exceeding 6.0m deep
1000mm dia caisson | M |  |  |  | 330
Exceeding 6.0m but not exceeding 7.5m deep
1000mm dia caisson | M |  |  |  | 340
Exceeding 7.5m but not exceeding 9.0m deep
1000mm dia caisson | M |  |  |  | 350
Exceeding 9.0m but not exceeding 10.5m deep
1000mm dia caisson | M |  |  | 1 | 360
Exceeding 10.5m but not exceeding 12.0m deep
1000mm dia caisson | M |  |  | 1 | 380
Exceeding 12.0m but not exceeding 13.5m deep
1000mm dia caisson | M |  |  | 1 | 400
Exceeding 13.5m but not exceeding 15.0m deep
1000mm dia caisson | M |  |  | 1 | 420
Exceeding 15.0m but not exceeding 16.5m deep
1000mm dia caisson | M |  |  | 1 | 440
Exceeding 16.5m but not exceeding 18.0m deep
1000mm dia caisson | M |  |  | 1 | 460
Exceeding 18.0m but not exceeding 19.5m deep
1000mm dia caisson | M |  |  | 1 | 480
Exceeding 19.5m but not exceeding 21.0m deep
1000mm dia caisson | M |  |  | 1 | 500
Extra over excavation through rock or bouldersin the following diamter caisson by using
explosive, break up, get up remove excavate rock deposit, spread and level where
directed within the site
1000mm diameter caisson (allow 3m rock only) | M |  |  |  | 638.7
Extra over for forming 1.0m belled out at the bottom of caisson
1000mm diameter caisson to 1400mm base dia (no according to drwg) | No |  |  | 1 | 450
Vibrated reinforcement concrete (Grade 30) tremie 1 as specified in caisson shaft (inclusive
overcasting 500mm) to
1000mm dia caisson | M |  |  |  | 260
Extra over for bell out to 1000mm dia caisson (no need according to drwg) | No |  |  | 1 | 300
Supply, fabricate and place steel reinforcement cage of following size and
installation of:
1000mm dia caisson
12Y25mm ditto (inclusive 1.0m starter bar) (416.45kg/no) | Kg |  |  |  | 3.7
R10 at 300 c/c spiral link (1850kg/no) | Kg |  |  |  | 3.8
Penetration drill test into bedrock at toe of caisson as directed by the S.O with pneumatic | No |  |  |  | 320
rock drill for a maximum depth of 4.5m, commencing at base of shaft, keeping records,
subsequently pressure grout up in cement and sand
Allow for submission of caisson records in triplicate duly signed by contractor and the | Item |  |  |  | 1000
S.O'`s representative and delivered to the S.O/Engineer as the work proceeds.
Constuction of extension circular columns from caisson head to capping beam | M |  |  |  | 780
level. Rate inclusive formworks, rebar and G30 concrete tremie 1 and fixing and
dismantling moulds.
Supply and install 2T16 starter bar at 0.5m c/c. Rate inclusive epoxy grout (Hilti) | No |  |  |  | 38
and drilling as per details.
Apply sprayed concrete (gunite) 150mm thick c/w 2 layers of BRC A6 and 2 rows | M2 |  |  |  | 260
75mm dia. Weepholes to inter space of caissons. Rate including mob and demob.
Supply and construct 1000x1200mm capping beams rate inclusive formworks and | M |  |  |  | 680
rebar works
Construct 9m soil Nail with Y25 in 100mm hole as tie back | No |  |  |  | 820
Supply all necessary materials, labour, equipments to construct 1200mm dia. Estimated 95m total wall length | No | 33 | 25000
Bridge
Bridge -900mm internal dia caisson pilling (2 nos)
-1000mm internal dia caisson pilling (20 nos)
-1200mm internal dia caisson pilling (6 nos)
Allow for the movements and set up of plants and equipment on the caisson foundation | No | 28 | 200 | 6 | 100
positions.
Construct concrete aprons to the approval of the Engineer to 1000mm diameter
caisson opening
900mm caisson pile (P3) | No | 2 | 160 |  | 100
1000mm caisson pile (P1) | No | 20 | 160 | 6 | 105
1200mm caisson pile (P2) | No | 6 | 180 |  | 120
Excavation only through whatever soil strata except rock, the following diameters for hand
dug caissons, remove excavated materials, deposits, spread and level where directed
within the site including casting 75mm to 150mm thick concrete lining for caissons
Not exceeding 1.5m deep
900mm dia caisson | M | 3 | 300 |  | 270
1000mm dia caisson | M | 30 | 300 | 9 | 300
1200mm dia caisson | M | 9 | 400 |  | 380
Exceeding 1.5m but not exceeding 3.0m deep
900mm dia caisson | M | 3 | 320 |  | 280
1000mm dia caisson | M | 30 | 320 | 9 | 310
1200mm dia caisson | M | 9 | 430 |  | 400
Exceeding 3.0m but not exceeding 4.5m deep
900mm dia caisson | M | 3 | 340 |  | 300
1000mm dia caisson | M | 30 | 340 | 9 | 320
1200mm dia caisson | M | 9 | 450 |  | 420
Exceeding 4.5m but not exceeding 6.0m deep
900mm dia caisson | M | 3 | 360 |  | 310
1000mm dia caisson | M | 30 | 360 | 9 | 330
1200mm dia caisson | M | 9 | 470 |  | 440
Exceeding 6.0m but not exceeding 7.5m deep
900mm dia caisson | M | 3 | 390 |  | 320
1000mm dia caisson | M | 30 | 390 | 9 | 340
1200mm dia caisson | M | 9 | 500 |  | 460
Exceeding 7.5m but not exceeding 9.0m deep
900mm dia caisson | M | 1 | 420 |  | 330
1000mm dia caisson | M | 1 | 420 | 9 | 350
1200mm dia caisson | M | 1 | 540 |  | 480
Exceeding 9.0m but not exceeding 10.5m deep
900mm dia caisson | M | 1 | 450 |  | 340
1000mm dia caisson | M | 1 | 450 | 8.5 | 360
1200mm dia caisson | M | 1 | 570 |  | 500
Exceeding 10.5m but not exceeding 12.0m deep
900mm dia caisson | M | 1 | 480 |  | 360
1000mm dia caisson | M | 1 | 480 | 4.1 | 380
1200mm dia caisson | M | 1 | 600 |  | 520
Exceeding 12.0m but not exceeding 13.5m deep
900mm dia caisson | M |  |  |  | 380
1000mm dia caisson | M |  |  | 1.5 | 400
1200mm dia caisson | M |  |  |  | 540
Exceeding 13.5m but not exceeding 15.0m deep
900mm dia caisson | M |  |  |  | 400
1000mm dia caisson | M |  |  | 0.7 | 420
1200mm dia caisson | M |  |  |  | 560
Exceeding 15.0m but not exceeding 16.5m deep
900mm dia caisson | M |  |  | 1 | 420
1000mm dia caisson | M |  |  | 1 | 440
1200mm dia caisson | M |  |  | 1 | 580
Exceeding 16.5m but not exceeding 18.0m deep
900mm dia caisson | M |  |  | 1 | 440
1000mm dia caisson | M |  |  | 1 | 460
1200mm dia caisson | M |  |  | 1 | 600
Exceeding 18.0m but not exceeding 19.5m deep
900mm dia caisson | M |  |  | 1 | 460
1000mm dia caisson | M |  |  | 1 | 480
1200mm dia caisson | M |  |  | 1 | 620
Exceeding 19.5m but not exceeding 21.0m deep
900mm dia caisson | M |  |  | 1 | 480
1000mm dia caisson | M |  |  | 1 | 500
1200mm dia caisson | M |  |  | 1 | 640
Extra over excavation through rock or bouldersin the following diamter caisson by using
explosive, break up, get up remove excavate rock deposit, spread and level where
directed within the site
900mm diameter caisson (allow 3m rock only) | M | 6 | 360 |  | 912
1000mm diameter caisson (allow 3m rock only) | M | 60 | 360 | 55 | 638.7
1200mm diameter caisson (allow 3m rock only) | M | 18 | 460 |  | 1650
Extra over for forming 1.0m belled out at the bottom of caisson
900mm diameter caisson to 1300mm base dia | No | 2 | 450 |  | 400
1000mm diameter caisson to 1400mm base dia | No | 20 | 450 |  | 450
1200mm diameter caisson to 1600mm base dia | No | 6 | 600 |  | 600
Vibrated reinforcement concrete (Grade 30) tremie 1 as specified in caisson shaft (inclusive
overcasting 500mm) to
900mm dia caisson | M | 15 | 330 |  | 300
Extra over for bell out to 900mm dia caisson | No | 2 | 300 |  | 260
1000mm dia caisson | M | 150 | 330 |  | 330
Extra over for bell out to 1000mm dia caisson | No | 20 | 300 |  | 300
1200mm dia caisson | M | 45 | 460 |  | 460
Extra over for bell out to 1000mm dia caisson | No | 6 | 415 |  | 415
Supply, fabricate and place steel reinforcement cage of following size and
installation of:
900mm dia caisson
11Y25mm ditto (inclusive 1.0m starter bar) (381.74kg/no) | Kg | 763.48 | 3.9 |  | 3.7
R12 at 300 c/c spiral link (848.75kg/no) | Kg | 1697.5 | 4 |  | 3.8
1000mm dia caisson
13Y25mm ditto (inclusive 1.0m starter bar) (451.15kg/no) | Kg | 9023 | 3.9 |  | 3.7
R12 at 300 c/c spiral link (943.05kg/no) | Kg | 18861 | 4 |  | 3.8
1200mm dia caisson
18Y25mm ditto (inclusive 1.0m starter bar) (624.67kg/no) | Kg | 3748.02 | 3.9 |  | 3.7
R12 at 300 c/c spiral link (1131.66kg/no) | Kg | 6789.96 | 4 |  | 3.8
Penetration drill test into bedrock at toe of caisson as directed by the S.O with pneumatic | No | 28 | 320 |  | 320
rock drill for a maximum depth of 4.5m, commencing at base of shaft, keeping records,
subsequently pressure grout up in cement and sand
Allow for submission of caisson records in triplicate duly signed by contractor and the | Item | 1 | 1000 | 1
S.O'`s representative and delivered to the S.O/Engineer as the work proceeds. (included)
Building
Building -900mm internal dia caisson pilling (81 nos)
-1200mm internal dia caisson pilling (7 nos)
Allow for the movements and set up of plants and equipment on the caisson foundation | No |  |  | 83 | 100
positions.
Shifting of caisson equipments and tools, from one unit foundation platform to next | No | 10 | 300
Construct concrete aprons to the approval of the Engineer to 1000mm diameter
caisson opening
900mm caisson pile | No |  |  | 83 | 100
1200mm caisson pile | No |  |  |  | 120
construct concrete aprons to the approval of the Engineer to 900mm dia & 1200mm dia caisson | No | 10 | 114
Excavation only through whatever soil strata except rock, the following diameters for hand
dug caissons, remove excavated materials, deposits, spread and level where directed
within the site including casting 75mm to 150mm thick concrete lining for caissons
Not exceeding 1.5m deep
900mm dia caisson | M |  |  | 124.5 | 270
900mm dia caisson | M | 103.5 | 260
1200mm dia caisson | M |  |  |  | 380
1200mm dia caisson | M | 28.5 | 360
Exceeding 1.5m but not exceeding 3.0m deep
900mm dia caisson | M |  |  | 124.5 | 280
900mm dia caisson | M | 103.5 | 260
1200mm dia caisson | M |  |  |  | 400
1200mm dia caisson | M | 28.5 | 360
Exceeding 3.0m but not exceeding 4.5m deep
900mm dia caisson | M |  |  | 124.5 | 300
900mm dia caisson | M | 103.5 | 290
1200mm dia caisson | M |  |  |  | 420
1200mm dia caisson | M | 28.5 | 400
Exceeding 4.5m but not exceeding 6.0m deep
900mm dia caisson | M |  |  | 118.48 | 320
900mm dia caisson | M | 103.5 | 290
1200mm dia caisson | M |  |  |  | 440
1200mm dia caisson | M | 28.5 | 400
Exceeding 6.0m but not exceeding 7.5m deep
900mm dia caisson | M |  |  | 89.93 | 340
900mm dia caisson | M | 103.5 | 320
1200mm dia caisson | M |  |  |  | 460
1200mm dia caisson | M | 28.5 | 440
Exceeding 7.5m but not exceeding 9.0m deep
900mm dia caisson (rate only) | M | 1 | 320 | 71.24 | 360
1200mm dia caisson (rate only) | M | 1 | 440 |  | 480
Exceeding 9.0m but not exceeding 10.5m deep
900mm dia caisson | M |  |  | 58.24 | 380
1200mm dia caisson | M |  |  |  | 500
Exceeding 10.5m but not exceeding 12.0m deep
900mm dia caisson | M |  |  | 40.55 | 400
1200mm dia caisson | M |  |  |  | 520
Exceeding 12.0m but not exceeding 13.5m deep
900mm dia caisson | M |  |  | 21.35 | 420
1200mm dia caisson | M |  |  |  | 540
Exceeding 13.5m but not exceeding 15.0m deep
900mm dia caisson | M |  |  | 8.8 | 440
1200mm dia caisson | M |  |  |  | 560
Exceeding 15.0m but not exceeding 16.5m deep
900mm dia caisson | M |  |  | 3.1 | 460
1200mm dia caisson | M |  |  |  | 580
Exceeding 16.5m but not exceeding 18.0m deep
900mm dia caisson | M |  |  | 0.4 | 480
1200mm dia caisson | M |  |  |  | 600
Exceeding 18.0m but not exceeding 19.5m deep
900mm dia caisson | M |  |  |  | 500
1200mm dia caisson | M |  |  |  | 620
Exceeding 19.5m but not exceeding 21.0m deep
900mm dia caisson | M |  |  |  | 520
1200mm dia caisson | M |  |  |  | 640
Extra over excavation through rock or bouldersin the following diamter caisson by using
explosive, break up, get up remove excavate rock deposit, spread and level where
directed within the site
900mm diameter caisson (allow 3m rock only) | M |  |  | 479.9 | 553.54
Extra over breaking through rock boulders and other obstruction by control rock blasting and pneumatic tools for touch up in 900mm dia caisson. (Provisional volume = 2.5m3/caisson) | M3 | 172.5 | 425
1200mm diameter caisson (allow 3m rock only) | M |  |  |  | 1000
Extra over breaking through rock boulders and other obstruction by control rock blasting and pneumatic tools for touch up in 1200mm dia caisson. (Provisional volume = 15m3/caisson) | M3 | 285 | 425
Extra over for forming 1.0m belled out at the bottom of caisson
900mm diameter caisson to 1300mm base dia | No |  |  | 74 | 265
900mm diameter caisson to 1300mm base dia | No | 69 | 327
1200mm diameter caisson to 1600mm base dia | No |  |  |  | 380
1200mm diameter caisson to 1600mm base dia | No | 19 | 380
Vibrated reinforcement concrete (Grade 30) tremie 1 as specified in caisson shaft (inclusive
overcasting 500mm) to
900mm dia caisson | M |  |  | 525.16 | 230
900mm dia caisson | M | 517.5 | 232
Extra over for bell out to 900mm dia caisson | No |  |  | 74 | 210
1200mm dia caisson | M |  |  |  | 380
1200mm dia caisson | M | 142.5 | 360
Extra over for bell out to 1000mm dia caisson | No |  |  |  | 350
Extra over for bell out to 1000mm dia caisson | No | 19 | 282
Supply, fabricate and place steel reinforcement cage of following size and
installation of:
900mm dia caisson
11Y25mm ditto (inclusive 1.0m starter bar) (381.74kg/no) | Kg |  |  | 26432.32 | 3.7
11Y25mm ditto (inclusive 1.0m starter bar) (381.74kg/no) | Kg | 30815.4 | 3.7
R12 at 300 c/c spiral link (848.75kg/no) | Kg |  |  | 4488.07 | 3.8
R12 at 300 c/c spiral link (848.75kg/no) | Kg | 2081.04 | 3.8
1200mm dia caisson
18Y25mm ditto (inclusive 1.0m starter bar) (624.67kg/no) | Kg |  |  |  | 3.7
18Y25mm ditto (inclusive 1.0m starter bar) (624.67kg/no) | Kg | 13898.5 | 3.7
R12 at 300 c/c spiral link (1131.66kg/no) | Kg |  |  |  | 3.8
R12 at 300 c/c spiral link (1131.66kg/no) | Kg | 606.67 | 3.8
Penetration drill test into bedrock at toe of caisson as directed by the S.O with pneumatic | No |  |  | 146 | 320
rock drill for a maximum depth of 4.5m, commencing at base of shaft, keeping records,
subsequently pressure grout up in cement and sand
to 900mm dia caisson pile | No | 69 | 280
to 1200mm dia caisson pile | No | 19 | 320
Allow for submission of caisson records in triplicate duly signed by contractor and the | Item | 1 |  | 1
S.O'`s representative and delivered to the S.O/Engineer as the work proceeds. (included)
VO1
Supply and construct Gunite wall 75mm thick with 1 layer BRC 6.5 wire mesh
and sprayed concrete applied to existing slope surface c/w Y12 tie pins as per
requirement. Rate including mob and demob of (150 psi/650CFM) air compressor.
(Area = (4.7 x 8.5) + (17.8 x 5.6) = 139.63m2 | m2 |  |  | 150 | 50.33
VO5
Blasting Permit Fix Fee (Feb'15 - July'15) | mth |  |  | 6 | 2500