## VO 09 (backup) (hidden)
CADANGAN MEMBINA DAN MENYIAPKAN 36 UNIT BANGUNAN INDUSTRI SESEBUAH 1 1/2 TINGKAT 100' X 200', (FASA 16B) DI ATAS LOT- LOT (98207 & 98029) - (98215 & 98037), PT. 69329 - PT. 69337, PT. 69338 - PT. 69355 DAN 3 UNIT PENCAWANG ELEKTRIK (PT. 69377, PT.69380 & PT.69409) DI ATAS SEBAHGAIAN LOT 69067 (LOT 19) & LOT 69099 (LOT 25) BANDAR BUKIT RAJA, OFF JALAN MERU, MUKIM KAMPAR, DAERAH KLANG UTARA (KU2), KLANG BANDAR DIRAJA, SELANGOR DARUL EHSAN UNTUK TETUAN SIME DARBY USJ DEVELOPMENT SDN BHD.
Supply Material And Labour To Construct insitu reinforce concrete drains and heavy duty drain cover slab for walkway and crossing | [9 empty] | 36
1.2
[5 empty] | 1 | 1
Item | Description | Ref | Unit | INFRA | EWWL | Infra | Rate | Omission (RM) | Addition (RM) | Rate | Amount | Qty | Rate | Amount | Qty | Rate | Amount
OMISSION
2.2 | RC DRAIN (CLOSED DRAIN)
| Supply material and labour to construct in situ reinforce concrete drains (with in situ drain cover slab). Rate to include excavation, blinding layer Grade C10/20, reinforced concrete Grade C25/20, formwork, reinforcement and compacted backfilling with suitable material. All works to be carried out as per specification and drawings. | [9 empty] | #REF!
2.2.1 | Bottom Width, B = 750 mm (Type C) but not exceeding 2.0m depth | BQ 11.2/1 | lin.m | 1 |  |  | 828.08 | -828.08 |  |  | #REF!
ADDITION
RC DRAIN (CLOSED DRAIN) WITHOUT SLAB
Excavate commencing from formation level and get out, part return, fill in and ram, deposit and spread in making up levels where directed within the site and remainder load and cart away
a | Trench for u-drain and cover slab | 6.1/1 | m3 | 1781.4195 |  |  | 12.5 |  | 22267.74
Mass concrete Grade 20, as specified in
b | 200mm thick blinding under U-drain bed | 6.1/1 | m3 | 4.2926 |  |  | 257.24 |  | 1104.22
Vibrated reinforced concrete Grade 25 - 20mm aggregate as described in :-
c | 100mm thk bed | 6.1/1 | m3 | 0.11464 |  |  | 267.43 |  | 30.66
d | 100mm thick wall | 6.1/1 | m3 | 0 |  |  | 267.43 |  | 0
| High tensile steel reinforcement bar as described in :- | [9 empty] | #REF! |  |  | 0 |  |  | 0
e | 10mm in bed and wall | 6.1/3 | kg | 0 |  |  | 3.67 |  | 0
[11 empty] | #REF! |  |  | 0 |  |  | 0
Sawn formwork as described to :-
f | Sides of bed | 6.1/3 | m2 | 0.4 |  |  | 35 |  | 14 |  | #REF!
g | Sides of walls | 6.1/3 | m2 | 7.7804 |  |  | 35 |  | 272.31
h | 300mm (Internal) wide x 150mm deep to invert half round glazed ware channel constructed of 60mm thick sides and bottom cast in 600mm lengths, bedded and jointed in cement and sand (1:3) mortar laid to falls including ends, angles and junctions | new rate | m | 0.095 |  |  | 60.14 |  | 5.71
j | 75mm Diameter PVC pipe 150mm long as weep hole cast through wall with and including surrounding one end of pipe with 230mm x 300mm filter backing consisting of selected aggregate (38mm to 75mm) and wrapped in with geotextile membrane | new rate | no | 0 |  |  | 13.3 |  | 0
[11 empty] | #REF! |  |  | 0 |  |  | 0
| DRAIN COVER SLAB FOR WALKWAY AND CROSSING | [9 empty] | #REF! |  |  | 0 |  |  | 0
|  |  |  | 0 | [6 empty] | #REF! |  |  | 0 |  |  | 0
Excavate commencing from formation level and get out, part return, fill in and ram, deposit and spread in making up levels where directed within the site and remainder load and cart away
a | Trench for u-drain and cover slab | 6.1/1 | m3 | 4.2926 |  |  | 12.5 |  | 53.66
Hardcore, consolidated and blinded to receive concrete
| 200mm (consolidated thickness), ground slab | 6.1/1 | m2 | 0 |  |  | 19.6 |  | 0 |  | #REF!
Mass concrete Grade 20, as specified in
| Blinding not exceeding 50mm thick under U-drain bed | 6.1/1 | m3 | 0 |  |  | 257.24 |  | 0
[11 empty] | #REF! |  |  | 0 |  |  | 0
| Vibrated reinforced concrete Grade 25 - 20mm aggregate as described in :- | [9 empty] | #REF! |  |  | 0 |  |  | 0
| 200mm thick cover slab | 6.1/2 | m3 | 0 |  |  | 267.43 |  | 0
High tensile steel reinforcement bar as described in :-
| 12mm in drain cover slab | 6.1/3 | kg | 0 |  |  | 3.67 |  | 0 |  | #REF! |  |  | 0 |  |  | 0
| 16mm in drain cover slab | 6.1/3 | kg | Qty/meter |  |  | 3.49 |  | #VALUE!
| 25mm in drain cover slab | 6.1/3 | kg | 0 |  |  | 3.49 |  | 0
Sawn formwork as described to :-
| Sides & soffit of drain cover slab | 6.1/3 | m2 | 0 |  |  | 35 |  | 0 |  | #REF!
| Sub-Total Amount (RM) | [6 empty] | -828.08 | #VALUE! | Total | #REF! |  | Total | 0 |  | Total | 0
| Total Amount (RM) | Nett Addition / Omission | [6 empty] | #VALUE!
[10 empty] | profit | #VALUE!
[10 empty] | % | #VALUE!

## VO15 040817
INFRASTRUCTURE
BACKLANE
To supply and lay 80mm thick interlocking pavers (Flexiplus - Black, Grey, Red) | m2 | 954 | 95.29 | 954 | 70
To supply and lay 80mm thick interlocking pavers (Flexiplus - Yellow, Peach) | m2 | 239 | 101.79 | 239 | 75
To supply and lay 80mm thick interlocking pavers (Flexiplus - Red Velvet) | m2 | 119 | 121.29 | 119 | 90
To supply and lay 80mm thick interlocking pavers (Flexiplus - Blue) | m2 | 119 | 216.19 | 119 | 163
WALKWAY
To supply and lay 60mm thick interlocking pavers (Flexipave 198 x 98 - Black colour), (Prime Paver 200 x 200 - Black, Grey Colour) | m2 | 985 | 71.5 | 985 | 50
To supply and lay 60mm thick interlocking pavers (Prime Paver 200 x 200 - Peach colour) | m2 | 30 | 71.5 | 30 | 52

## Sheet1
Material
50mm thk sand bedding | m2 | 3.3
3.3

## VO 02 (2) (hidden)
CADANGAN MEMBINA DAN MENYIAPKAN 36 UNIT BANGUNAN INDUSTRI SESEBUAH 1 1/2 TINGKAT 100' X 200', (FASA 16B) DI ATAS LOT- LOT (98207 & 98029) - (98215 & 98037), PT. 69329 - PT. 69337, PT. 69338 - PT. 69355 DAN 3 UNIT PENCAWANG ELEKTRIK (PT. 69377, PT.69380 & PT.69409) DI ATAS SEBAHGAIAN LOT 69067 (LOT 19) & LOT 69099 (LOT 25) BANDAR BUKIT RAJA, OFF JALAN MERU, MUKIM KAMPAR, DAERAH KLANG UTARA (KU2), KLANG BANDAR DIRAJA, SELANGOR DARUL EHSAN UNTUK TETUAN SIME DARBY USJ DEVELOPMENT SDN BHD.
VO 03 Upgrade Incoming Cold Water Pipe To Rainwater Harvesting Tank
1.2
[5 empty] | 1 | 1 |  |  |  |  | Maxitech
Item | Description | Ref | Unit | Type A | EWWL | Infra | NOU | Rate | Omission (RM) | Addition (RM) | Rate | Amount | Qty | Rate | Amount | Qty | Rate | Amount
OMISSION
To upgrade existing incoming pipe size from the water meter upto the tee-off point to domestic storage tank (underground pipe from 25mm diameter to 32mm diameter
| 25mm diameter PPR PN 16 pipe | BQ-12/M/1 | m | 42 |  |  | 36 | 42 | -63504 |  | 40 | -60480
ADDITION
To upgrade existing incoming pipe size from the water meter upto the tee-off point to domestic storage tank (underground pipe from 25mm diameter to 32mm diameter
| 32mm diameter PPR PN 16 pipe | BQ-12/M/1 | m | 42 |  |  | 36 | 48.3 |  | 73029.6 | 46 | 69552 |  |  | 0 |  |  | 0
[8 empty] | 0 | [6 empty] | 0 |  |  | 0
Extra over for incoming pipe to rainwater harvesting tank (underground pipework only). Pipe to tee-off from the incoming pipe to the domestic water tank
| 25mm diameter PPR PN16 pipe |  | m | 40 |  |  | 36 | 42 |  | 60480 | 40 | 57600
| Sub-Total Amount (RM) | [7 empty] | -63504 | 133509.6 | Total | 66672 |  | Total | 0 |  | Total | 0
| Total Amount (RM) | Nett Addition / Omission | [7 empty] | 70005.6
[11 empty] | profit | 3333.6
[11 empty] | % | 5%
Note on E17: Chow Pak Shin: 0.491 + 17.645 + 21.651 + 2.068
Note on M17: Chow Pak Shin: didn’t submit this rate during tender stage, as unit rate don’t have allow for PN16, therefore, mr.chan use PN20 to claim it
Note on M22: Chow Pak Shin: ms lam confirm with maxitech verbally
Note on M25: Chow Pak Shin: didn’t submit this rate during tender stage, as unit rate don’t have allow for PN16

## Slab Construction (hidden)
Project: R36 | [9 empty] | Unit |  | 1 | 0.395 | 0.617 | 0.888 | 1.579 | 2.467 | 3.854 | 6.315 | [7 empty] | 24 |  |  | 0.0061667 |  | 0.222 | 0.395 | 0.617 | 0.888 | 1.579
Item:Reinforcement
Location: Blk C (R)
|  |  | Bar | [16 empty] | Links
Item | Ref | Length | Type No | Shape | Dia | Spacing | Bar No | a | b | c | qty | Total | 8 | 10 | 12 | 16 | 20 | 25 | 32 | CC | Type No | Dia | Spacing | Length | a | b | e | Bar No | nou | Total | Shape | 6 | 8 | 10 | 12 | 16
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Grd flr | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | a |  |  |  | d
| S6 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | b |  | c
| top | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 36 Units
ver | 1 | 2.78 | 1 |  | 12 | 0.2 | 15 | 0.103 | 0.796 |  | 1 | 13.485 | 0 | 0 | 13.485 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | L | W | H | NOS | NOU | Exc | Conc | Fwk | Harcore | T10 | T12
| 2 | 2.78 | 1 |  | 12 | 0.2 | 15 | 0.85 |  |  | 1 | 12.75 | 0 | 0 | 12.75 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | a | 1.93 | 0.154 | 0.15 | 1 | 36 | 1.605 | 1.605 | 10.422 | 10.6999 | 12777.3864 | 17649.2771
hor |  | 0.796 | 1 |  | 10 | 0.2 | 5 | 0.05 | 2.78 | 0.05 | 1 | 14.4 | 0 | 14.4 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | b | 7.6 | 0.154 | 0.2 | 1 | 36 | 8.4269 | 8.4269 | 54.72 | 42.1344
|  | 0.85 | 1 |  | 10 | 0.2 | 5 | 0.05 | 2.78 | 0.05 | 1 | 14.4 | 0 | 14.4 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | c | 7.6 | 0.154 | 0.2 | 1 | 36 | 8.4269 | 8.4269 | 54.72 | 42.1344
| btm | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | d | 7.74 | 0.154 | 0.2 | 1 | 36 | 8.5821 | 8.5821 | 55.728 | 42.9106
ver | 3 | 2.78 | 1 |  | 12 | 0.2 | 15 | 0.103 | 2.901 |  | 1 | 45.06 | 0 | 0 | 45.06 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2.901 | 1 |  | 10 | 0.2 | 16 | 0.05 | 2.78 | 0.05 | 1 | 46.08 | 0 | 46.08 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | Total |  |  |  |  | 27.0409 | 27.0409 | 175.59 | 137.8793 | 12777.3864 | 17649.2771
| S1-1-1.5/A-A1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| top | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ver | 1 | 7.6 | 1 |  | 12 | 0.2 | 39 | 0.128 | 1.207 |  | 1 | 52.065 | 0 | 0 | 52.065 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| 2 | 7.6 | 1 |  | 12 | 0.2 | 39 | 1.2 |  |  | 1 | 46.8 | 0 | 0 | 46.8 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | wihtout drawing
hor |  | 1.207 | 1 |  | 10 | 0.2 | 7 | 0.1 | 7.6 | 0.1 | 1 | 54.6 | 0 | 54.6 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1.2 | 1 |  | 10 | 0.2 | 7 | 0.1 | 7.6 | 0.1 | 1 | 54.6 | 0 | 54.6 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ver | 3 | 7.6 | 1 |  | 12 | 0.2 | 39 | 0.128 | 3.954 |  | 1 | 159.198 | 0 | 0 | 159.198 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
hor |  | 3.954 | 1 |  | 10 | 0.2 | 21 | 0.1 | 7.6 | 0.1 | 1 | 163.8 | 0 | 163.8 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| S1-1-1.5/A1-B | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| top | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
hor | 1 | 3.908 | 1 |  | 12 | 0.2 | 21 | 1.2 |  |  | 1 | 25.2 | 0 | 0 | 25.2 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| 2 | 3.91 | 1 |  | 12 | 0.2 | 21 | 1.258 | 0.128 |  | 1 | 29.106 | 0 | 0 | 29.106 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ver |  | 1.2 | 1 |  | 10 | 0.2 | 7 | 0.1 | 3.91 | 0.1 | 1 | 28.77 | 0 | 28.77 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1.258 | 1 |  | 10 | 0.2 | 7 | 0.1 | 3.91 | 0.1 | 1 | 28.77 | 0 | 28.77 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| btm | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
hor | 1 | 3.91 | 1 |  | 10 | 0.2 | 21 | 7.959 | 0.128 |  | 1 | 169.827 | 0 | 169.827 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| 2 | 7.959 | 1 |  | 12 | 0.2 | 41 | 0.1 | 3.908 | 0.1 | 1 | 168.428 | 0 | 0 | 168.428 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 575.247 | 552.092 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | Chow | 0 | 354.9274 | 490.2577 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | PG | 4.6126 | 3639.3988 | 5322.1557 | 27.4391
[12 empty] | BQ | 2 | 5262 | 7675 | 9
[12 empty] | Difference | -4.6126 | -3284.4714 | -4831.898 | -27.4391
(R8)
Note on J13: Chow Pak Shin: assume
Note on L13: Chow Pak Shin: assume
Note on J14: Chow Pak Shin: assume
Note on L14: Chow Pak Shin: assume
Note on J17: Chow Pak Shin: assume
Note on L17: Chow Pak Shin: assume

## Column and Stump (hidden)
Compose Chow Qty
Stump and Column | Stump | grd | 1st | 2nd | 3rd | 4th | Total
Concrete | 36.61 | 81.7 | 52.32 | 50.88 | 50.6 |  | 272.11
Rebar | [6 empty] | 0
R8 | 361.13 | 63.26 | 215.5 | 650.19 | 2494.25 |  | 3784.33
R6 |  | 0 |  |  |  |  | 0
R10 |  | 3827.67 | 2344.02 | 1575.36 |  |  | 7747.05
T32 | 21899.13 | [5 empty] | 21899.13
T25 | 19176.42 | 30498.59 | 22871.98 | 10754.37 |  |  | 83301.36
T20 | 0 | 230.88 |  | 346.82 |  |  | 577.7
T16 | 0 |  | 355.65 | 244.51 | 133.37 |  | 733.53
T12 | 59.11 |  | 71.18 | 355.91 | 2093.94 |  | 2580.14
T10 | 4065.17 | [5 empty] | 4065.17
Formwork | 36.61 | 672 | 537.6 | 526.4 | 521.36 |  | 2293.97