## SC Sales G - Sewerage
Description | Unit | Qty | AA Cost | Qty | CGS VENTURE
|  |  | Rate |  | Rate
OMIISION
INFRA WORKS
Excavation trench commencing from reduced level, get out, part return, fill in, ram, deposit and spread in marking to levels where directed within the site remainder load and cart away from site (The tenderer shall include in his rates for excavation and cutting of all materials encountered except for rock and provision of all necessary temporary shoring/ sheet piling, strutting and dewatering)
300mm Diameter pipe 600mm wide bed not exceeding 1.50m deep; average 1.35m deep | m | 76 | -20 | 76 | -10
Ditto exceeding 1.50m deep but not exceeding 3.00m deep; average 1.80m deep | m | 56 | -24 | 56 | -13.5
Ditto ; average 2. 10m deep | m | 59 | -28 | 59 | -16
Ditto; average 2.40m deep | m | 51 | -32 | 51 | -18
Ditto ; average 2.55m deep | m | 29 | -36 | 29 | -20
Ditto; average 2.85m deep | m | 38 | -40 | 38 | -22
600mm x 300mm thick x 20mm diameter aggregate as described well compacted under 300mm diameter pip (measured separately) half embecled in trench | m | 312 | -30 | 312 | -12
300mm Diameter Class 'EX'vitrified clay sewer pipe as described to B-S- 65 laid and jointed in trench complete with all necessary excavation, bend pipe, concrete bedding and surround | m | 312 | -350.9091 | 312 | -220
Reinforced concrete Grade 20 as described to receive selected earth backfill | m3 | 46 | -120 | 46 | -5
MANHOLE
Precast concrete Grade 20 circular manhole constructed of standard reinforced concrete chamber ring with cement mortar fill; laid on minimum400mm thick reinforced concrete Grade 25 as described base: reinforced with 2 layers of BRC A7 fabric reinforcement with 50mm thick Grade 15mm concrete blinding: 150mm thick concrete Grade 20 encasement all round and including taper top (eccentric cone) painted internally with two layers of coat epoxy tar; concrete make up piece; lining internalIV with 20mm thick of high alumina cement mortar~ precast high alumina cement concrete channel and forming sulphate resisting concrete benching; including all necessary formwork and reinforcement: half round straights chan el and fittings: forming opneninq to receive pipes; excavation and cutting of all material encountered (except for rock), provision of all necessary temporary shoring/ sheet piling strutting dewatering: disposal of excavated materials: and building in ends of pipes and fixing accessories as per Drawing No.ARSB/1609/SW/DTU02/R00
Overall size 1200mm x 1200mm x average 1.20m deep internally | No | 2 | -2000 | 2 | -2400
Ditto 1.35m deep internally | No | 1 | -2200 | 1 | -2600
Ditto 1.50m deep internally | No | 1 | -2400 | 1 | -2800
Ditto 2.25m deep internally | No | 1 | -2600 | 1 | -4200
Ditto 2.40m deep internally | No | 1 | -3000 | 1 | -4500
Ditto 2.55m deep internally | No | 2 | -3500 | 2 | -4800
MANHOLE COVER
Ductile iron manhole cover and frame overall size 840mm x 840mm all as per drawing No: ARSB/1609/SW/DTL/01/R00 | No | 8 | -600 | 8 | -500
Allow for connection to existing manhole/ sewer lines including all necessary excavation and additional pipe length, accessories and fittings to entire satisfaction of the S.O. | item | 1 | -15000 | 1 | -5000
Conduct CCTV inspection of the completed sewer line as directed by the S.O. (Rates shall include for provision of all equipment, setting up of equipment, labour, materials, production of reports, video tapes, mobilisation, demobilisation and movements from one location to another location including all necessary work associated with the CCTV inspection | item | 1 | -5000 | 1 | -5000
Allow for testing the whole of the soil drainage, manhole and etc. as described making good any defects and leave everything in perfect working order to the satisfaction of S.O. and Local Authorities | item | 1 | -5000 | 1 | -3000
Allow for cleaning, desilting, connection, testing and inspection by Local Authority on any laid sewerage works including making good all works disturbed and defects, paying all fees in connection with inspection and leave everything in perfect working order to the satisfaction of the S.O. and Local Authorities | item | 1 | -3000 | 1 | -3000
|  | 0 |  | 0
ADDITION
INFRA WORKS
Excavation trench commencing from reduced level, get out, part return, fill in, ram, deposit and spread in marking to levels where directed within the site remainder load and cart away from site (The tenderer shall include in his rates for excavation and cutting of all materials encountered except for rock and provision of all necessary temporary shoring/ sheet piling, strutting and dewatering)
300mm Diameter pipe 600mm wide bed not exceeding 1.50m deep; average 1.35m deep | m | 76 | 20 | 0 | 10
Ditto exceeding 1.50m deep but not exceeding 3.00m deep; average 1.80m deep | m | 56 | 24 | 85 | 13.5
Ditto ; average 2. 10m deep | m | 59 | 28 | 43.87 | 16
Ditto; average 2.40m deep | m | 51 | 32 | 0 | 18
Ditto ; average 2.55m deep | m | 29 | 36 | 0 | 20
Ditto; average 2.85m deep | m | 38 | 40 | 0 | 22
600mm x 300mm thick x 20mm diameter aggregate as described well compacted under 300mm diameter pip (measured separately) half embecled in trench | m | 312 | 30 | 280.87 | 12
300mm Diameter Class 'EX'vitrified clay sewer pipe as described to B-S- 65 laid and jointed in trench complete with all necessary excavation, bend pipe, concrete bedding and surround | m | 312 | 350.9091 | 196.87 | 220
Reinforced concrete Grade 20 as described to receive selected earth backfill | m3 | 46 | 120 | 126.41 | 5
MANHOLE
Precast concrete Grade 20 circular manhole constructed of standard reinforced concrete chamber ring with cement mortar fill; laid on minimum400mm thick reinforced concrete Grade 25 as described base: reinforced with 2 layers of BRC A7 fabric reinforcement with 50mm thick Grade 15mm concrete blinding: 150mm thick concrete Grade 20 encasement all round and including taper top (eccentric cone) painted internally with two layers of coat epoxy tar; concrete make up piece; lining internalIV with 20mm thick of high alumina cement mortar~ precast high alumina cement concrete channel and forming sulphate resisting concrete benching; including all necessary formwork and reinforcement: half round straights chan el and fittings: forming opneninq to receive pipes; excavation and cutting of all material encountered (except for rock), provision of all necessary temporary shoring/ sheet piling strutting dewatering: disposal of excavated materials: and building in ends of pipes and fixing accessories as per Drawing No.ARSB/1609/SW/DTU02/R00
Overall size 1200mm x 1200mm x average 1.20m deep internally | No | 2 | 2000 | 2 | 2400
Ditto 1.35m deep internally | No | 1 | 2200 | 0 | 2600
Ditto 1.50m deep internally | No | 1 | 2400 | 1 | 2800
Ditto 2.25m deep internally | No | 1 | 2600 | 1 | 4200
Ditto 2.40m deep internally | No | 1 | 3000 | 0 | 4500
Ditto 2.55m deep internally | No | 2 | 3500 | 0 | 4800
MANHOLE COVER
Ductile iron manhole cover and frame overall size 840mm x 840mm all as per drawing No: ARSB/1609/SW/DTL/01/R00 | No | 8 | 600 | 6 | 500
Allow for connection to existing manhole/ sewer lines including all necessary excavation and additional pipe length, accessories and fittings to entire satisfaction of the S.O. | item | 1 | 15000 | 1 | 5000
Conduct CCTV inspection of the completed sewer line as directed by the S.O. (Rates shall include for provision of all equipment, setting up of equipment, labour, materials, production of reports, video tapes, mobilisation, demobilisation and movements from one location to another location including all necessary work associated with the CCTV inspection | item | 1 | 5000 | 1 | 5000
Allow for testing the whole of the soil drainage, manhole and etc. as described making good any defects and leave everything in perfect working order to the satisfaction of S.O. and Local Authorities | item | 1 | 5000 | 1 | 3000
Allow for cleaning, desilting, connection, testing and inspection by Local Authority on any laid sewerage works including making good all works disturbed and defects, paying all fees in connection with inspection and leave everything in perfect working order to the satisfaction of the S.O. and Local Authorities | item | 1 | 3000 | 1 | 3000
|  | 0 |  | 0
VARIATION ORDER NO.01
EXCAVATION
Extra over for excavation
300mm diameter pipe 600mm wide bed ; average 3.15m deep | m | 0 | 24 | 68 | 24
Ditto ; average 3.45m deep | m | 0 | 26 | 0 | 26
Ditto ; average 3.75m deep | m | 0 | 28 | 84 | 28
300mm DIAMETER DUCTILE IRON PIPE
Extra over for 300mm diameter ductile iron sewer pipe and jointed in trench complete with all necessary excavation, bend pipe, concrete bedding and surround (MH4 to MH5) | m | 0 | 400 | 84 | 400
MANHOLE
Overall size 1200mm x 1200mm x average 3.30m deep | nos | 0 | 6100 |  | 6100
Ditto 3.45m deep internally | nos | 0 | 6300 | 1 | 6300
Ditto 3.60m deep internally | nos | 0 | 6500 | 1 | 6500
EXTRA OVER FOR STANDARD BACKDROP
300mm Diameter Backdrop
Supply and install standard backdrop include all
For drop E 1.00m and N.E. 200m | nos | 0 | 3000 | 1 | 3000
VARIATION ORDER NO.02
RFV SEWERAGE WORKS
Mobilisation and demobilisation | Item | 1 | 6000 | 1 | 5000
demolition of MH 5 | Item | 1 | 6000 | 1 | 5000
Divertion of existing 750mm RCP sewerline | Item | 1 | 12000 | 1 | 10000
Temporary protection work - Sheet pile | Item | 1 | 24000 | 1 | 20000
Supply and lay 300mm diameter ductile iron pipe | m | 20 | 600 | 20 | 500
Construction 1 nos 150mm diameter precast manhole at existing sewerline 750mm RCP depth 3.95m | item | 1 | 9600 | 1 | 8000
Cleaning of blockage sewerage - Using water jetting truck | day | 2 | 3000 | 11 | 1800