## VO02 180118
Project: | R618, Bukit Raja
Subcontractor: Suwi Composites Sdn Bhd
SubContract: FRP Window & Door
Re: | VO No. 2 | [5 empty] | Recommended for APVO
|  |  | MC Cost |  |  | 0 |  |  | Qty |  | AA Recommended |  |  | mutual Agreed | Remark
Item | Description | Unit | Total Qty | Rate | Amount | Total Qty | sub con Rate | Amount | Chow TO | CGS | Total Qty | Rate | Amount | Rate
VO No. 2
Omission
| TOTAL OMISSION |  |  |  | 0 |  |  | 0 |  |  |  |  | 0
Addition
FRP Composite Window
1 | Size: 2100mm x 750mm (H) | no | 0 | 0 | 0 | 2 | 356 | 712 |  |  | 2 | 356 | 712
1 | Brickwall | m2 | 3.15 | 10 | 31.5 | 0 | 0 | 0 |  |  | 0 | 0 | 0
2 | Plastering | m2 | 3.15 | 13.99 | 44.07 | 0 | 0 | 0 |  |  | 0 | 0 | 0
| TOTAL ADDITION |  |  |  | 75.57 |  |  | 712 |  |  |  |  | 712
| Total Amount |  |  |  | 75.57 |  |  | 712 |  |  |  |  | 712
| Cost Saving (RM) | [6 empty] | -636.43 |  |  |  |  | -636.43
VO Claim Status:
Amount recommend by QS:
| Amount received: | 0
Date receive:
Remarks:
Approval by:
Contract Manager: Ms Lam
General Manager (Central Region): Mr Khew
Project Director: Mr Chuah

## Taking Off
Opening for Lift Motor Room
Description | No | Length | Height | Area (m2)
Brickwall | 2 | 2.1 | 0.75 | 3.15
Plastering | 2 | 2.1 | 0.75 | 3.15