## V.O 1
Project: | Proposed Development On Part of Lot 435, 520, 524, 2875, 2876, 5780 (Lot Lama 523), PT 135, PT 138 And Part of Lot428, 429, Mukim 14, SPS, Bukit Tambun, Penang. (BKT1)
LA ref no: | 19102016/BKT1/37
Date: | 2017-06-01
Subject : | V.O No.1
Item | Description | Unit |  | VB COST |  | Qty | VB |  | Sykt Majujaya Utama Sdn.Bhd.
|  |  | Quantity | Rate | Amount |  | Rate | Amount | Rate | Amount
Omission
Bus Stop
A | Supply and install bus stop overall size 6000mm (L) x 3000mm (W) x 2222mm (H) complete with all structural works, architectural works, signages and etc as shown in approved Local Authority Drawings | item | 1 | 20000 | 20000 | 1 | -20000 | -20000 | -18000 | -18000
B | Miscellaneous Works As required by the local Authority
Road lay-by
B.I | Excavation works | item | [5 empty] | included |  | included
B.2 | Road base | item | [5 empty] | included |  | included
B.3 | Premix works | item | [5 empty] | included |  | included
B.4 | Road marking | item | [5 empty] | included |  | included
B.5 | Oku ramp | item | [5 empty] | included |  | included
B.6 | Road kerb | item | [5 empty] | included |  | included
B.7 | Scupper drain | item | [5 empty] | included |  | included
B.8 | Signages | item | [5 empty] | included |  | included
Addition
Bus Stop
A | Supply and install bus stop overall size 6000mm (L) x 3000mm (W) x 2222mm (H) complete with all structural works, architectural works, signages and etc as shown in approved Local Authority Drawings | item | 1 | 20000 | 20000 | 1 | 20000 | 20000 | 18000 | 18000
B | Miscellaneous Works As required by the local Authority
Road lay-by
B.I | Excavation works | item | [7 empty] | included
B.2 | Road base | item | [7 empty] | included
B.3 | Premix works | item | [7 empty] | included
B.4 | Road marking | item | [7 empty] | included
B.5 | Oku ramp | item | [7 empty] | included
B.6 | Road kerb | item | [7 empty] | included
B.7 | Scupper drain | item | [7 empty] | included
B.8 | Signages | item | [7 empty] | included
|  | Total Amount (RM) |  |  | 40000 |  |  | 0 |  | 0
Note on F16: Siti Fadhilah BT Kamaruddin: Contribution Total Sum
Note on F32: Siti Fadhilah BT Kamaruddin: Contribution Total Sum