## SubBQ
Project : | SB135
Subcontractor : | Teh William
SubContract Works : | Sub-contract for External Water Recticulation Works
Re : | Subcon Claim BQ |  |  |  |  | Estimate
claim no. 01
Item | Description | Unit | Rate | Total Qty | Amount | Previous Qty | Claimed Qty | Claimed Amt
| SECTION NO. 3 - WATER RECTICULATION |  | ELECTRONFUSION JOINT
[5 empty] | 0 |  |  | 0
| Excavate trench commencing from reduced level, get out, part return, fill in, ram, deposit and spread in making up levels where directed within the site, remainder load and cart away from site including all necessary dewatering system, temporary shoring and steel sheet piles as directed by the S.O. (The tenderer shall include in his rates for excavation and cutting of all materials encountered except for rock) |  |  |  | 0 |  |  | 0
A | 63mm Diameter pipe; 513mm wide bed not exceeding 1.50m deep; average 0.932m deep | m | 5 | 1260 | 6300 |  | 336 | 1680
[5 empty] | 0 |  |  | 0
B | 125mm Diameter pipe; 575mm wide not exceeding 1.50m deep, average 0.963m deep | m | 5 | 219 | 1095 |  |  | 0
[5 empty] | 0 |  |  | 0
C | 180mm Diameter pipe; 630mm wide not exceeding 1.50m deep, average 0.99m deep | m | 5 | 2188 | 10940 |  | 336 | 1680
[5 empty] | 0 |  |  | 0
| Approved HDPE as described laid and jointed in trench including all necessary joints all to satisfaction of the Engineer and PBA |  |  |  | 0 |  |  | 0
D | 63mm HDPE pipe | m | 28 | 1260 | 35280 |  | 336 | 9408
[5 empty] | 0 |  |  | 0
E | Extra over for stop cock | No | 350 | 21 | 7350 |  |  | 0
[5 empty] | 0 |  |  | 0
F | Extra over for 180mm x 63mm x 180mm tee | No | 450 | 20 | 9000 |  |  | 0
[5 empty] | 0 |  |  | 0
H | 125mm HDPE pipe | m | 85 | 219 | 18615 |  |  | 0
[5 empty] | 0 |  |  | 0
J | Extra over for 45 degree bend | No | 210 | 1 | 210 |  |  | 0
[5 empty] | 0 |  |  | 0
K | Extra over for 90 degree bend | No | 210 | 10 | 2100 |  |  | 0
[5 empty] | 0 |  |  | 0
L | Extra over for 180mm x 125mm x 180mm tee | No | 550 | 1 | 550 |  |  | 0
[5 empty] | 0 |  |  | 0
M | Extra over for 180mm ~ 125mm reducer | No | 300 | 2 | 600 |  |  | 0
[5 empty] | 0 |  |  | 0
N | 180mm HDPE pipe | m | 120 | 2188 | 262560 |  | 336 | 40320
[5 empty] | 0 |  |  | 0
P | Extra over for 22.5 degree bend | No | 320 | 11 | 3520 |  |  | 0
[5 empty] | 0 |  |  | 0
Q | Extra over for 45 degree bend | No | 320 | 12 | 3840 |  |  | 0
[5 empty] | 0 |  |  | 0
R | Extra over for 90 degree bend | No | 320 | 27 | 8640 |  | 4 | 1280
[5 empty] | 0 |  |  | 0
S | Extra over for 180mm x 180mm x 180mm tee | No | 450 | 22 | 9900 |  | 4 | 1800
[5 empty] | 0 |  |  | 0
| Concrete Grade 20 as described thrust block laid in trench around fittings including additional excavation and formwork |  |  |  | 0 |  |  | 0
A | Overall size 533mm x 610mm x 610mm; for 22.5 degree bend | No | 0 | 11 | Included |  |  | 0
0
B | Overall size 553mm x 553mm x 762mm; for 45 degree bend | No | 0 | 1 | Included |  |  | 0
0
C | Overall size 610mm x 610mm x 838mm; for 45 degree bend | No | 0 | 12 | Included |  |  | 0
0
D | Overall size 610mm x 457mm x 762mm; for 90 degree bend | No | 0 | 10 | Included |  |  | 0
0
E | Overall size 762mm x 610mm x 762mm; for 90 degree bend | No | 0 | 27 | Included |  | 4 | 0
0
F | Overall size 914mm x 838mm x 838mm; for 180-125 reducer | No | 0 | 2 | Included |  |  | 0
0
G | Overall size 914mm x 838mm x 838mm; for 180-63-180 Tee | No | 0 | 20 | Included |  |  | 0
0
H | Overall size 914mm x 838mm x 838mm; for 180-125-180 Tee | No | 0 | 1 | Included |  |  | 0
0
J | Overall size 914mm x 838mm x 838mm; for 180-180-180 Tee | No | 0 | 22 | Included |  |  | 0
[5 empty] | 0 |  |  | 0
A | 100mm Diameter Inlet pillar hydrant with 2 nos.63.5mm diameter outlets complete with 100mm diameter x 750mm long double flanged extension piece with webs, 100mm diameter D.I. double flanged 90 degree duck foot bend complete with concrete thrust block and all necessary reducers,excavation, concrete, formworks and other fittings; all as per Drawing No. 63/12/LA/WS(G) -2/2 | No | 2000 | 22 | 44000 |  | 4 | 8000
[5 empty] | 0 |  |  | 0
B | 100mm Diameter sluice valve jointed to HDPE pipe (measured separately) and complete with 150mm thick granular bedding, 300mm thick sand filling, 50mm thick granular fill, PC chamber including cast iron box to the approval of the S.O. and PBA all as per Drawing No. 63/12/LA/WS(G) -2/2 | No | 600 | 21 | 12600 |  | 4 | 2400
[5 empty] | 0 |  |  | 0
C | 125mm Diameter sluice valve ditto | No | 1200 | 2 | 2400 |  |  | 0
[5 empty] | 0 |  |  | 0
D | 180mm Diameter sluice valve ditto | No | 1600 | 16 | 25600 |  | 4 | 6400
[5 empty] | 0 |  |  | 0
E | 100mm Diameter double flange scour valve jointed to ductile iron pipe (measured separately) and complete with fittings, concrete thrust block and including valve chamber and cover with all necessary excavation to the approval of the S.O. and PBA | No | 1200 | 0 | Rate Only |  |  | 0
[5 empty] | 0 |  |  | 0
F | Supply and install 50mm double orifice air valve as described complete with flanged butterfly valve, fittings and including valve chamber and cover to the approval of the S.O. and PBA | No | 1200 | 2 | 2400 |  |  | 0
| c/w 177.3mm s-bend | No | 3850 | 2 | 7700 |  |  | 0
[5 empty] | 0 |  |  | 0
G | 50mm Diameter ABS Class 9 tubing as pipe/valve marker 750mm high, complete with end cap, flange, 245mm x 35mm high orange colour reflective stickers, 150 x 150mm high AWAS sticker with bottom end of tubing fixed to and including concrete footing; to the approval of PBA | No | 50 | 63 | 3150 |  |  | 0
[5 empty] | 0 |  |  | 0
| WATER MAIN CONNECTION |  |  |  | 0 |  |  | 0
A | Allow for supply and installation of 28mm diameter stainless steel pipes, tapping saddle, standard brass main ferrule cock, nipple, bush, lockable valve, one no. "T", 20mm brass stopcock with stainless steel standing pipe and all other necessary accessories for the connection of the water reticulation, main to individual unit tap off point setting on Grade 20 mass concrete bed including all necessary excavation and backfilling all to PBA's approval including provision of water sub-meter | No | 325 | 214 | 69550 |  | 32 | 10400
[5 empty] | 0 |  |  | 0
B | 150mm meter position overall size 3940mm x 1000mm complete with 2 nos.D.I. bend, sluice valve support with 115mm x 225mm clay brickwall, D.I. collar, adaptor tail piece, 'Helix' meter, lengthener support with 225mm x 225mm clay brick on 150mm thick RC base slan with 14 nos 12mm mild steel reinforcement bar at 300mm centres and 6 nos 10mm mild steel reinforcement bar at 190mm centres and all necessary reducers, excavation, concrete, formworks and other fittings; all as per Drawing No. 63/12/LA/WS - 8/9 | No | 3500 | 2 | 7000 |  |  | 0
[5 empty] | 0 |  |  | 0
C | 100mm meter position overall size 3270mm x 1000mm, ditto | No | 2850 | 2 | 5700 |  |  | 0
[5 empty] | 0 |  |  | 0
D | 3 nos of 20mm stainless steel meter position with 20mm lockable valve and additional stopcock complete with address plate, all as per Drawing No. 63/12/LA/WS - 8/9 | No | 450 | 1 | 450 |  |  | 0
[5 empty] | 0 |  |  | 0
E | Allow for connection to existing water lines including all necessary excavation and additional pipe length, accessories and fittings to entire satisfaction of the S.O. and all application fees for digging permits, deposits imposed by Local Authorities, fees chargeable by relevant Authorities for temporary disconnection/ connection and compliance with all statutory requirement | Item | 6500 | 1 | 6500 |  |  | 0
[5 empty] | 0 |  |  | 0
F | Allow for all other works not listed above but shown on drawings or necessary to ensure completion of Water Reticulation |  |  |  | 0 |  |  | 0
| a) 88.8mm GI "C" 63mm tee | m | 0 | 65 | Included |  |  | 0
| b) Extra over for 180mm socket | no | 150 | 320 | 48000 |  |  | 0
| c) Extra over for 125mm socket | no | 110 | 32 | 3520 |  |  | 0
[5 empty] | 0 |  |  | 0
| RELOCATION OF EXISTING WATER MAIN |  |  |  | 0 |  |  | 0
| Excavate trench commencing from reduced level, get out, part return, fill in, ram, deposit and spread in making up levels where directed within the site, remainder load and cart away from site including all necessary dewatering system, temporary shoring and steel sheet piles as directed by the S.O. (The tenderer shall include in his rates for excavation and cutting of all materials encountered except for rock) |  |  |  | 0 |  |  | 0
A | 177.3mm Diam pipe; 627.3mm wide bed not exceeding 1.50m deep; average 0.989m deep | m | 5 | 190 | 950 |  | 160 | 800
[5 empty] | 0 |  |  | 0
B | 345.4mm Diameter pipe; 795.4mm wide bed not exceeding 1.50m deep; average 1.073m deep | m | 5 | 385 | 1925 |  |  | 0
[5 empty] | 0 |  |  | 0
| Approved mild steel concrete lined pipe to B.S. 534 as described with and including welded collar joints as described wrapped externally with bitumen to satisfaction of the Engineer and PBA |  |  |  | 0 |  |  | 0
C | 177.3mm Diameter pipe with plain ended joint | m | 190 | 190 | 36100 |  | 160 | 30400
[5 empty] | 0 |  |  | 0
D | 345.4mm Diameter pipe with plain ended joint | m | 320 | 385 | 123200 |  |  | 0
[5 empty] | 0 |  |  | 0
E | Extra over for 45 degree bend | No | 450 | 1 | 450 |  |  | 0
[5 empty] | 0 |  |  | 0
F | Extra over for 345.4mm x 345.4mm x 177.3mm plain ended tee | No | 600 | 1 | 600 |  |  | 0
[5 empty] | 0 |  |  | 0
G | Allow for end cap to cap off 100mm diameter pipe | No | 1200 | 1 | 1200 |  |  | 0
[5 empty] | 0 |  |  | 0
H | Allow for end cap to cap off existing 180mm diameter pipe ditto | No | 300 | 1 | 300 |  |  | 0
[5 empty] | 0 |  |  | 0
J | Allow for end cap to cap off existing 300mm diameter pipe ditto | No | 300 | 4 | 1200 |  |  | 0
[5 empty] | 0 |  |  | 0
| Concrete Grade 20 as described thrust block laid in trench around fittings incldg additional excavation and fornwork |  |  |  | 0 |  |  | 0
A | Overall size 838mm x 838mm x 914mm; for 45 degree bend | No | 80 | 1 | 80 |  |  | 0
[5 empty] | 0 |  |  | 0
B | Overall size 1524mm x 1219mm x 991mm; for 345.4-345.4-177.3 Tee | No | 80 | 1 | 80 |  |  | 0
[5 empty] | 0 |  |  | 0
C | Supply and install 50mm double orifice air valve | No | 1200 | 1 | 1200 |  |  | 0
| c/w 177.3mm S- Bend | No | 3850 | 1 | 3850 |  |  | 0
[5 empty] | 0 |  |  | 0
D | 300mm Diameter sluice valve | No | 2700 | 2 | 5400 |  |  | 0
[5 empty] | 0 |  |  | 0
E | 50mm diameter ABS class 9 tubing as pipe/valve marker 750mm high | No | 50 | 3 | 150 |  |  | 0
[5 empty] | 0 |  |  | 0
F | Allow for all other works not listed above but shown on drawings or necessary to ensure completion of water reticulation |  |  |  | 0 |  |  | 0
a) | Testing and comissioning | item |  | 1 | Included |  |  | 0
b) | 6" S.V complete with chamber | no | 1800 | 5 | Rate Only |  |  | 0
c) | 345.4mm S-Bend | no | 4850 | 2 | Rate Only |  |  | 0
d) | 177.3mm S.Bend | no | 3850 | 2 | Rate Only |  |  | 0
e) | 345.4mm ms connection to existing 3000 A.C | no | 6500 | 537 | Rate Only |  |  | 0
f) | 177.3mm ms connection to existing 100m A.C | no | 2700 | 88 | Rate Only |  |  | 0
g) | 345.4mm MS connection to existing 180m HDPE | no | 2700 | 1 | Rate Only |  |  | 0
[5 empty] | 0 |  |  | 0
0
[5 empty] | 795755 |  |  | 114568
|  |  |  | Original Contract Sum: | 795755 |  | Total Claim Sum: | 114568 | 0 | 0
[7 empty] | VO | 0
[7 empty] | Total | 114568
[8 empty] | 0 | -114568
on hold for material backcharges