## Sheet1
Original Contract
WBLF
Class F1 formwork finish, to,
Side of pile caps | m2 | 2421 | -19.37 | 2421 | -18.5
Sides of column stumps | m2 | 882 | -19.37 | 882 | -18.5
Sides of ground beams | m2 | 11911 | -19.37 | 11911 | -18.5
Sides of ground slab | m2 | 394 | -19.37 | 394 | -18.5
Edge of drop not exceeding 100mm thick | m2 | 21 | -19.37 | 21 | -18.5
Class F1 formwork finish, to,
Edge of aprons, exceeding 150mm but not exceeding
300mm high. | m2 | 92 | -19.37 | 92 | -18.5
Edge of ramps, exceeding 150mm but not exceeding
300mm high. | m2 | 91 | -19.37 | 91 | -18.5
FRAME
Class F1 formwork finish, to
Sides of columns | m2 | 7117 | -19.37 | 7117 | -18.5
Sides and soffit of beams | m2 | 7819 | -19.37 | 7819 | -18.5
Sides and soffit of roof beams | m2 | 3062 | -19.37 | 3062 | -18.5
Sides and soffit of upper roof beams | m2 | 3357 | -19.37 | 3357 | -18.5
UPPER FLOORS
Class F1 formwork finish, to
Soffit of slabs. | m2 | 3100 | -19.37 | 3100 | -18.5
ROOF CONSTRUCTION
Class F1 formwork finish, to,
Soffit of suspended roof slab | m2 | 1040 | -19.37 | 1040 | -18.5
Sides of upstand beam | m2 | included | -19.37 | included | -18.5
STAIRCASE CONSTRUCTION
Class F1 formwork, to,
Sides and soffit of landing beams. | m2 | 43 | -19.37 | 43 | -18.5
Sloping Soffit of staircase. | m2 | 187 | -19.37 | 187 | -18.5
Soffit of landing slab. | m2 | 79 | -19.37 | 79 | -18.5
Raking open edge of staircase, 345mm wide
(extreme width). | m2 | 89 | -19.37 | 89 | -18.5
Riser to staircase, exceeding 100mm but not
exceeding 250mm high. | m2 | 140 | -19.37 | 140 | -18.5
Edges of landing slab, exceeding 100mm but not
exceeding 150mm high | m2 | 16 | -19.37 | 16 | -18.5
SUNDRIES
Class F1 formwork finish, to,
Sides of plinth | m2 |  | -19.37 |  | -18.5
CONCRETOR
WBLFF
Hardcore, consolidated and blinded to receive concrete
100mm (consolidated thickness), ground slab. | m2
Mass concrete Grade 20, as specified in
Blinding not exceeding 50mm thick under pile caps | m2 | 663 | -2.5 | 663 | -4
Blinding not exceeding 50mm thick under ground
beams | m2 | 1395 | -2.5 | 1395 | -4
PE sheet
Damp proof membrane, well lapped in the joints and
sealed with approved pressure sensitive tape, turned
up against wall for at least the full thickness of floor
(measured nett: allow for laps and turn up).
One layer of 0.25mm thick polythene sheet, under
floor slab. | m2 | 11155 | -1 | 11155 | -0.6
Vibrated reinforced concrete Grade 30, as specified in,
Pile caps | m3 | 397 | -25 | 397 | -19.5
Vibrated reinforced concrete Grade 25, s specified in,
Column stumps (Provisional) | m3 | 76 | -25 | 76 | -19.5
Ground beams | m3 | 784 | -25 | 784 | -19.5
Ground slab, exceeding 100mm but not exceeding
150mm thick | m3 | 83 | -25 | 83 | -19.5
Ground slab, exceeding 150mm but not exceeding
300mm thick | m3 | 2120 | -25 | 2120 | -19.5
Apron and Ramps
Hardcore, consolidated and blinded to receive
concrete
150mm (consolidated thickness) under aprons. | m2 | 322 | -2.5 | 322 | -4.5
150mm (consolidated thickness) under ramps | m2 | 194 | -2.5 | 194 | -4.5
Mass concrete Grade 20, as specified in
Blinding, not exceeding 50mm thick under aprons | m2 | 323 | -2.5 | 323 | -4
Blinding, not exceeding 50mm thick under ramps | m2 | 194 | -2.5 | 194 | -4
Vibrated reinforced concrete Grade 25, as
specified, in;
Aprons | m3 | 54 | -25 | 54 | -19.5
Ramps | m3 | 29 | -25 | 29 | -19.5
FRAME
Vibrated reinforced concrete Grade 25, as
specified, in,
Columns. | m3 | 653 | -25 | 653 | -19.5
Beams. | m3 | 635 | -25 | 635 | -19.5
Roof beams. | m3 | 281 | -25 | 281 | -19.5
Upper roof beams. | m3 | 326 | -25 | 326 | -19.5
UPPER FLOOR
Vibrated reinforced concrete Grade 25, as
specified, in,
Floor, not exceeding 150mm thick. | m3 | 441 | -25 | 441 | -19.5
Floor, exceeding 150mm - 300mnn thick. | m3 | 16 | -25 | 16 | -19.5
ROOF CONSTRUCTION
Flat Roof
Vibrated reinforced concrete Grade 25, as specified,
in,
Suspended roof slab exceeding 100mm thick but
not exceeding 150mm thick | m3 | 145 | -25 | 145 | -19.5
Upstand Beam | m3 | included | -25 | included | -19.5
STAIRCASE CONSTRUCTION
Vibrated reinforced concrete Grade 25, as specified, in,
Staircase. | m3 | 52 | -25 | 52 | -19.5
Landing beams. | m3 | 2 | -25 | 2 | -19.5
Landing slabs, exceeding 100mm but not exceeding
150mm thick. | m3 | 16 | -25 | 16 | -19.5
SUNDRIES
The following in Concrete Plinths at Water Tank
Vibrated reinforced concrete Grade 25, as specified
in,
Plinth | m3 | included in rb | -25 | included in rb | -19.5
50mm Lean concrete beneath tie beam | m2
50mm lean concrete beneath wall base | m2
SETTING OUT | unit | 18 | -55 | 18 | -250
LEVELING OF EARTH FOR (INCLUDING PUMP WATER AND COMPACT): | unit | 18 |  | 18 | -400
A) FOOTING | m2
B) PILECAP | m3
C) GROUND BEAM | m3
D) GROUND SLAB | m2
SUPERVISION OF EXCAVATION FOR WBGL | unit | 18 | -45 | 18 | -250
PROVIDE SPACER BLOCK FOR BAR BENDER | unit | 18 | -30 | 18 | -120
Remeasurement of VO02 (Pile Cap to Footing)
Mass concrete Grade 20, as specified in
Blinding not exceeding 50mm thick under pile caps | m2 | 204.08 | -2.5 | 204.08 | -4
Blinding not exceeding 50mm thick under footings | m2 | 1911.36 | -2.5 | 1911.36 | -4
Vibrated reinforced concrete Grade 30, as specified in,
Pile caps | m3 | 112.27 | -25 | 112.2703 | -19.5
Footings | m3 | 929.96 | -25 | 929.96 | -19.5
Class F1 formwork finish, to,
Side of pile caps | m2 | 482.37 | -19.37 | 482.36 | -18.5
Side of footings | m2 | 1607.32 | -19.37 | 1607.32 | -18.5
Remeasurement of VO04 (Additional Blinding to GF Slab)
Work Below Lowest Floor Finish
Mass concrete Grade 20, as specified in
Blinding not exceeding 50mm thick under ground slab | m2 | 9818.82 | -2.5 | 9818.82 | -4
TOTAL OMISSION
ADDITION
Original Contract
WBLF
Class F1 formwork finish, to, |  |  |  | Follow LA (as previously omitted in VO02)
Side of pile caps | m2 | 2421 | 19.37 | 2421 | 18.5
Sides of column stumps | m2 | 882 | 19.37 | 882 | 18.5
Sides of ground beams | m2 | 11911 | 19.37 | 8297.52 | 18.5
Sides of ground slab | m2 | 394 | 19.37 | 302.24 | 18.5
Edge of drop not exceeding 100mm thick | m2 | 21 | 19.37 | 21.47 | 18.5
Class F1 formwork finish, to,
Edge of aprons, exceeding 150mm but not exceeding
300mm high. | m2 | 92 | 19.37 | 71.28 | 18.5
Edge of ramps, exceeding 150mm but not exceeding
300mm high. | m2 | 91 | 19.37 | 35.64 | 18.5
FRAME
Class F1 formwork finish, to
Sides of columns | m2 | 7117 | 19.37 | 6978.24 | 18.5
Sides and soffit of beams | m2 | 7819 | 19.37 | 6707.5 | 18.5
Sides and soffit of roof beams | m2 | 3062 | 19.37 | 3581.16 | 18.5
Sides and soffit of upper roof beams | m2 | 3357 | 19.37 | 3678.8 | 18.5
UPPER FLOORS
Class F1 formwork finish, to
Soffit of slabs. | m2 | 3100 | 19.37 | 2489.36 | 18.5
ROOF CONSTRUCTION
Class F1 formwork finish, to,
Soffit of suspended roof slab | m2 | 1040 | 19.37 | 543.23 | 18.5
Sides of upstand beam | m2 | included | 19.37 |  | 18.5
STAIRCASE CONSTRUCTION
Class F1 formwork, to,
Sides and soffit of landing beams. | m2 | 43 | 19.37 | 32.53 | 18.5
Sloping Soffit of staircase. | m2 | 187 | 19.37 | 203.58 | 18.5
Soffit of landing slab. | m2 | 79 | 19.37 | 77.22 | 18.5
Raking open edge of staircase, 345mm wide
(extreme width). | m2 | 89 | 19.37 | 78.83 | 18.5
Riser to staircase, exceeding 100mm but not
exceeding 250mm high. | m2 | 140 | 19.37 | 105.25 | 18.5
Edges of landing slab, exceeding 100mm but not
exceeding 150mm high | m2 | 16 | 19.37 | 21.24 | 18.5
SUNDRIES
Class F1 formwork finish, to,
Sides of plinth | m2 |  | 19.37 |  | 18.5
CONCRETOR
WBLFF
Hardcore, consolidated and blinded to receive concrete
100mm (consolidated thickness), ground slab. | m2
Mass concrete Grade 20, as specified in |  |  |  | Follow LA (as previously omitted in VO02)
Blinding not exceeding 50mm thick under pile caps | m2 | 663 | 2.5 | 663 | 4
Blinding not exceeding 50mm thick under ground
beams | m2 | 1395 | 2.5 | 1357.1 | 4
PE sheet
Damp proof membrane, well lapped in the joints and
sealed with approved pressure sensitive tape, turned
up against wall for at least the full thickness of floor
(measured nett: allow for laps and turn up).
One layer of 0.25mm thick polythene sheet, under
floor slab. | m2 | 11155 | 1 | 11154.67 | 0.6
Vibrated reinforced concrete Grade 30, as specified in, |  |  |  | Follow LA (as previously omitted in VO02)
Pile caps | m3 | 397 | 25 | 397 | 19.5
Vibrated reinforced concrete Grade 25, s specified in,
Column stumps (Provisional) | m3 | 76 | 25 | 76 | 19.5
Ground beams | m3 | 784 | 25 | 769.12 | 19.5
Ground slab, exceeding 100mm but not exceeding
150mm thick | m3 | 83 | 25 | 1669.42 | 19.5
Ground slab, exceeding 150mm but not exceeding
300mm thick | m3 | 2120 | 25 |  | 19.5
Apron and Ramps
Hardcore, consolidated and blinded to receive
concrete
150mm (consolidated thickness) under aprons. | m2 | 322 | 2.5 | 328.32 | 4.5
150mm (consolidated thickness) under ramps | m2 | 194 | 2.5 | 194.4 | 4.5
Mass concrete Grade 20, as specified in
Blinding, not exceeding 50mm thick under aprons | m2 | 323 | 2.5 | 328.32 | 4
Blinding, not exceeding 50mm thick under ramps | m2 | 194 | 2.5 | 194.4 | 4
Vibrated reinforced concrete Grade 25, as
specified, in;
Aprons | m3 | 54 | 25 | 53.87 | 19.5
Ramps | m3 | 29 | 25 | 29.16 | 19.5
FRAME
Vibrated reinforced concrete Grade 25, as
specified, in,
Columns. | m3 | 653 | 25 | 649.84 | 19.5
Beams. | m3 | 635 | 25 | 777.39 | 19.5
Roof beams. | m3 | 281 | 25 | 317 | 19.5
Upper roof beams. | m3 | 326 | 25 | 357.6 | 19.5
UPPER FLOOR
Vibrated reinforced concrete Grade 25, as
specified, in,
Floor, not exceeding 150mm thick. | m3 | 441 | 25 | 336.76 | 19.5
Floor, exceeding 150mm - 300mnn thick. | m3 | 16 | 25 | 32.43 | 19.5
ROOF CONSTRUCTION
Flat Roof
Vibrated reinforced concrete Grade 25, as specified,
in,
Suspended roof slab exceeding 100mm thick but
not exceeding 150mm thick | m3 | 145 | 25 | 72.29 | 19.5
Upstand Beam | m3 | included | 25 |  | 19.5
STAIRCASE CONSTRUCTION
Vibrated reinforced concrete Grade 25, as specified, in,
Staircase. | m3 | 52 | 25 | 57.91 | 19.5
Landing beams. | m3 | 2 | 25 | 1.88 | 19.5
Landing slabs, exceeding 100mm but not exceeding
150mm thick. | m3 | 16 | 25 | 15.44 | 19.5
SUNDRIES
The following in Concrete Plinths at Water Tank
Vibrated reinforced concrete Grade 25, as specified
in,
Plinth | m3 | included in rb | 25 |  | 19.5
50mm Lean concrete beneath tie beam | m2
50mm lean concrete beneath wall base | m2
SETTING OUT | unit | 18 | 55 | 18 | 250
LEVELING OF EARTH FOR (INCLUDING PUMP WATER AND COMPACT): | unit | 18 |  | 18 | 400
A) FOOTING | m2
B) PILECAP | m3
C) GROUND BEAM | m3
D) GROUND SLAB | m2
SUPERVISION OF EXCAVATION FOR WBGL | unit | 18 | 45 | 18 | 250
PROVIDE SPACER BLOCK FOR BAR BENDER | unit | 18 | 30 | 18 | 120
Remeasurement of VO02
Mass concrete Grade 20, as specified in
Blinding not exceeding 50mm thick under pile caps | m2 | 204.08 | 2.5 | 2115.45 | 4
Blinding not exceeding 50mm thick under footings | m2 | 1911.36 | 2.5 |  | 4
Vibrated reinforced concrete Grade 30, as specified in,
Pile caps | m3 | 112.27 | 25 | 1042.23 | 19.5
Footings | m3 | 929.96 | 25 |  | 19.5
Class F1 formwork finish, to,
Side of pile caps | m2 | 482.37 | 19.37 | 2246.6 | 18.5
Side of footings | m2 | 1607.32 | 19.37 |  | 18.5
Remeasurement of VO04 (Additional Blinding to GF Slab) - Subcon missed out to claim
Work Below Lowest Floor Finish
Mass concrete Grade 20, as specified in
Blinding not exceeding 50mm thick under ground slab | m2 | 9818.82 | 2.5 | 2150.28 | 4